## PBNICG1
Action Item | Action | Owner | Contributors | Target date | Status | Result | Comment | Reference to TOR
1/1 | States are encouraged to consider including military aerodromes where international civil operations are taking place into the Regional Air Navigation Plan (RANP) and State PBN Implementation Plan. | All |  | 2015-12-18 | Closed | States are invited to consider this action | ICG1-WP2 | 1-b
1/2 | To provide Fiji with the draft amendment to Annex 11 regarding the flight procedures regulatory framework. | Noppadol Pringvanich | Erwin Lassooij | 2015-06-11 | Closed | State Letter 2015/22 | ICG1-WP4 | 2
1/3 | To coordinate with APAC FPP Steering committee about the need for procedure design course for helicopters. | Noppadol Pringvanich |  | 2015-11-30 | Open | WP will be submitted to APAC FPP SC during their annual meeting in Nov 2015 | Need was raised by Maldives (Ibrahim Hameed) | 1-a
1/4 | To review and enhance the PBN Implementation Progress Report form, such that it can fulfill global and regional PBN reporting requirements. | IlaitiaTabakaucoro | Hermizan Jumari, Xiang Xiao Jun, Zhang Ying, Frederic Lecat, Huho Ha | 2015-06-11 | Closed | See. PBNICG/2 WP/04 | ICG1WP1/WP9 | 1-a
1/5 | APAC Regional Office to issue a State letter to request APAC States and Administrations not having submitted yet a PBN plan to do so, provide PBN POCs,and consider forming sub-regional groups as necessary. | Frederic Lecat | Noppadol Pringvanich | 2015-06-11 | Closed | See State Letter AP052-15 | As per 11Mar. 15, States/Adm. not having submitted are: Afghanistan, Bhutan, Brunei Darussalam, China Macao, Cook Islands, Kiribati, Marshall Islands, Micronesia (Federated States of), Nauru, Palau, Samoa, Solomon Islands, Timor-Leste, Vanuatu | 1-b
1/6 | With regard to action 1/5, Fiji in cooperation with RSO to assist Pacific Islands States who have not developed or submitted their PBN Implementation Plan. | IlaitiaTabakaucoro | Noppadol Pringvanich | 2015-12-18 | Open | Fiji will coordinate this in June 2015 | ICG1-WP10 | 1-b
1/7 | With regard to action 1/5, to coordinate with Brunei Darussalam for the PBN implementation including the submission of State PBN Implementation Plan. | Noppadol Pringvanich |  | 2015-06-11 | Open | Planning for PBN implemenation support for Brunei is being coordinated between ICAO HQ and ICAO APAC RSO | ICG1-WP10 | 1-b
1/8 | Maldives to share with Myanmar the benefits/experience of implementation of PBN (RNP 1) Domestic routes. | Ibrahim Hameed | Noppadol Pringvanich | 2015-08-14 | Closed | See Maldives presentation during 2015 APAC PBN Seminar | ICG1 - IP04 | 1-c
1/9 | To remind PBN Study Group through APAC RO about the need for the requirement for ARNP Charting Criteria to support the application of ARNP to be available by as soon as possible, preferably by the end of 2015. | Frederic Lecat | Joe Lam | 2015-06-11 | Closed | Updated recievd from ICAO HQ. The charting for ARNP is available but still need for the enroute part. Job cards for panels have been developed | ICG1 - IP8 | 2
1/10 | To invite PBN Study Group to develop/review guidance material on PBN when used to support User Preferred Route (UPR)/Flex Track operations, especially regarding database management. | Frederic Lecat | IlaitiaTabakaucoro, Noppadol Pringvanich | 2015-06-11 | Closed |  | ICG1-IP12 | 1-c, 2
1/11 | APAC Regional Office to issue a State letter to request APAC States and Administrations to update their PBN Implementation Plan by the end of 2016. | Frederic Lecat | Noppadol Pringvanich | 2015-06-11 | Closed | See State Letter AP052-15 | ICG1-WP5 | 1-a, b
1/12 | To review the targets and metrics which are related to PBN in the APAC Seamless ATM Plan and provide inputs, if any to the APAC Regional Office before the next review cycle of the APAC Seamless ATM Plan. | Noppadol Pringvanich | Frederic Lecat | The next review cycle of the APAC Seamless ATM Plan. | Open | See PBNICG/2 WP/08. PBNICG agrees to form a small group to work on the proposal for update. | ICG1-IP6 | 3
1/13 | States to report analysis of benefits and challenges with implementing PBN. | All | Noppadol Pringvanich | 2015-09-30 | Closed | See PBN Seminar 2015 |  | 1-d
1/14 | To collect issues regarding the use of ICARD system by the States and deliver them to the relevant section of ICAO HQ through ICAO RO. | Joe Lam | Zhang Ying | 31-Mar-16 PBNICG/3 | Open |  | ICG1-IP6 | 1-a, 2
1/15 | ICAO to clarify relevant criteria of 5LNC and route designation allocation in respect of all the parameters applied e.g. similar pronunciation definition and to provide clear detailed guidelines on using ICARD system. On the other hand to enhance the performance of ICARD application. | ICAO |  | 2015-06-11 | Closed |  | ICG1-IP6 | 1-a, 2
1/16 | To stipulate clearly the logic, the criteria for ICARD parameters and supplement with clear detail guidelines; and to enhance the service provided by ICARD regarding the similar pronunciation and ICARD application performance. | ICAO |  | 2015-06-11 | Closed |  | ICG1-IP6 | 1-a, 2
1/17 | To improve and review the draft ‘PBN-in-a-page' (see comment part). | Joe Lam, IlaitiaTabakaucoro | Hu Ho Ha, all participants for inputs | 2015-06-11 | Closed | See. PBNICG/2 WP/02 | ICG1- Flimsy01 - Add a column on database requirements, and isolate COM/SUR/NAV as columns | 1-a, 2
1/18 | States to send their views as to the necessity and feasibility to have a national military PBN operational approval mechanism. | All | Noppadol Pringvanich | 2015-12-18 | Open |  | ICG1-WP8 | 2
1/19 | RSO to coordinate with Australia regarding RNP10 for A461. | Noppadol Pringvanich | Ian Mallett | 2015-06-11 | Open | Discussion is now on-going at SCS MTRF meeting which will be conducted in July 2015. Australia will be coordinated following the meeting. | ICG1-IP01 | 1-c
1/20 | To provide information from SASP to PBNICG about RNP AR and ILS simultaneous operations. | Ian Mallett |  | 2015-06-11 | Closed | See presentations from PBN Seminar 2015 | ICG1-IP01 | 1-a
1/21 | APAC RSO to draft a Statement Of Work (SOW) for sub-regional groups to engage in sub-regional review of ATS routes, propose draft material and associated work plan to the relevant informal and formal (ICAO) bodies as needed, in order to ensure extensive review and consistency. | Noppadol Pringvanich | IlaitiaTabakaucoro, Frederic Lecat | 2015-06-11 | Open | See PBNICG/2 Flimsy/1 | ICG1-IP07 | 1-c
1/22 | To better scope and enhance the PBN checklist for RNP APCH, SIDs/STARs and develop a draft checklist for PBN en-route. | Joe Lam, IlaitiaTabakaucoro | Ibrahim Hameed, M.S.Athar, Hermizan Jumari, Noppadol Pringvanich, Frederic Lecat, Huho Ha | 2015-06-11 | Closed | See PBNICG/2 WP/03 | ICG1-WP7 | 1-a, 2
1/23 | Considering the low level of current fleet capability for RF, to request PBN Study Group to consider RF as an optional requirement for ARNP during the transition period. | Frederic Lecat | Joe Lam | 2015-06-11 | Closed | This proposeal is being considered by PBNSG. Alternate options are being evaluated. | ICG1-WP11 | 2
1/24 | To check that any reference to 12.6 NM separation be removed from RANP. | Frederic Lecat |  | 2015-06-11 | Closed |  | ICG1-IP5 | 3

## PBNICG2
Action Item | Action | Owner | Contributors | Target date | Status | Result | Comment | Reference to TOR
2/1 | ICAO to coordinate with EASA on their PBN roadmap, with a particular focus on RF. | Erwin Lassooij | Noppadol Pringvanich, Frederic Lecat | 2016-02-26 | Open |  | ICG2-IP04 | 1-b
2/2 | ICAO RO to plan the integration of option A in the Seamless ATM reporting scheme. | Frederic Lecat |  | 2016-02-26 | Open |  | ICG2-WP04 | 1-d, 2
2/3 | ICAO RSO to assess the feasibility of an engine for assisting desirous States with computing their metrics as per option B. | Noppadol Pringvanich |  | 2016-02-26 | Open |  | ICG2-WP04 | 1-d, 2
2/4 | ICAO APAC RSO to coordinate with the stakeholders in Sri Lanka and facilitate a possible discussion on the PBN parallel route concept between Male (VRMM) and Colombo (VCBI). | Noppadol Pringvanich |  | 2015-10-15 | Open |  | ICG2-WP10 | 1-c
2/5 | ICAO provide PBN-in-a-page to the relevant Panels and Study Groups for the review and provide related guidance on route spacing. | Erwin Lassooij | Noppadol Pringvanich, Frederic Lecat | 2015-07-13 | Open |  | ICG2-WP02, with Draft Decision 2/1 | 1-a. 2
2/6 | IATA to provide the estimated population and the forecast growth for every 5 years period of all new navigation specifications. | IATA | Erwin Lassooij, Noppadol Pringvanich, Frederic Lecat | 2015-12-18 | Open |  | ICG2-WP05 | 1-b, 2
2/7 | States, through ICAO HQ, to prepare a paper to PBN study group specifying needs and operational requirements for establishing new or updating PBN nav spec and PBN Manual to support 0.3 NM outside final approach segment. | Joe Lam | Erwin Lassooij, Huho Ha | 2015-11-16 | Open |  | ICG2-WP05 | 1-b, 2
2/8 | ICAO requested to provide chart specimen for ARNP in TMA and Approach. | Erwin Lassooij | Noppadol Pringvanich | 2015-12-18 | Open |  | ICG2-WP05 | 1-b, 2
2/9 | The small group to propose amendments regarding PBN related elements to the Seamless ATM plan targets and Seamless ATM implementation guidance on the targets and guidance material. | Frederic Lecat | IlaitiaTabakaucoro, Joe Lam, Len Wicks, Noppadol Pringvanich, Huho Ha, IATA, States | The next review cycle of the APAC Seamless ATM Plan. | Open |  | ICG2-WP08 | 3
2/10 | ICAO HQ to share the key points of the Seminar to appropriate SGs and Panels. | Erwin Lassooij |  | 2015-12-18 | Open |  | ICG2-WP09 | 1-a
2/11 | ICAO to deliver PBN Operational Approval training material for new PBN navigation specifications RNP 2 and Advanced RNP, by September 2015 and training delivery by Dec 2015 | ICAO | Noppadol Pringvanich, Frederic Lecat | 2015-12-18 | Open |  | ICG2-WP09 | 1-a, b
2/12 | ICAO to consider conduct the education conference in conjunction with PBNICG/4. | ICAO | Noppadol Pringvanich, Frederic Lecat | by PBNICG/4 | Open |  | ICG2-WP09 | 1-a, b
2/13 | Note that the IATA course is currently available. ICAO to consider conduct the training in conjunction with future DGCA conference. | ICAO | Noppadol Pringvanich, Frederic Lecat | 2015-10-15 | Open |  | ICG2-WP09 | 1-a, b
2/14 | Noppadol and Erwin to inform the FPP SC so that they include this into future procedure design training provisions. | Noppadol Pringvanich, Erwin Lassooij |  | 2015-11-26 | Open |  | ICG2-WP09 | 1-a, b
2/15 | ICAO to distribute training material (including CBT) to IFALPA for its members, IATA and Regulators. | ICAO |  | 2015-12-18 | Open |  | ICG2-WP09 | 1-a, b
2/16 | RSO to coordinate with Airbus and Boeing to summarize fleet readiness status for PBN and GBAS into one table. | Noppadol Pringvanich | Huho Ha, Airbus, Boeing | 2015-10-15 | Open |  | ICG2-WP09 | 1-a, b
2/17 | PBNICG members to submit paper on their needs for quality assurance and licensing needs by next PBNICG/3. | All | IlaitiaTabakaucoro | 2016-02-26 | Open |  | ICG2-WP09 | 1-a, b, 2
2/18 | ICAO to consider providing information on current progress of Panel works regarding guided visual procedures. | Erwin Lassooij | Noppadol Pringvanich | 2016-02-26 | Open |  |  | 1-b, 2
2/19 | State to present a paper on their implementation experience regarding guided visual procedures. | All |  | 2016-02-26 | Open |  |  | 1-b, 2
2/20 | States are invited to provide papers on PBN Implementation status to future PBNICG meetings. | All |  | 2016-02-26 | Open |  |  | 1-a
2/21 | States to use the template of the PBN progress reporting form (option A) to summarize and submit the PBN activities to regularly report PBN implementation status as soon as possible and preferably before July 2015. | All | Frederic Lecat | 2015-07-24 | Open |  |  | 1-d
D2/1 | Draft Decision 2/1 - PBN in a page That, The PBN-in-a-page document be adopted as regional supporting material and be published on the ICAO RO website after the review by relevant Panels and Study Group as well as ICAO. | [5 empty] | ICG2-WP02 | 1-a. 2
D2/2 | Draft Decision 2/2 - PBN Procedure Safety Assessment Checklists and Record of Hazard Template That, 1. The PBN Procedure Safety Assessment Checklists and Record of Hazard Template be adopted as regional supporting material; and 2. The checklists and template be published on the ICAO RO website. | [5 empty] | ICG2-WP03 | 1-b