## Sheet1
JOHANNESBURG FCWM GROUP
Tributary | State | Automated FPL system yes/no | System Vendor | will this be upgraded? | software implementation date | testing date | operational commissioning | ANSP testing date | users testing date | Automated ATM system yes/no | will this be upgraded? | System Vendor | software implementation date | testing date | operational commissioning | ANSP testing date | users testing date | Accepting FPL in new and present format date | Accepting FPL in NEW format only (15 NOV 2012?) | Operational contact person | tel / mobile | e-mail
FAJS | SOUTH AFRICA | Yes | THALES | yes | 2012-06-01 | 1-6 June 2012 | 2012-06-06 | 7-30 June 2012 | 1 July 2012-14 November 2012 | yes | yes | THALES | same as AIM system | same as AIM system | same as AIM system | same as AIM system | same as AIM system | 2012-09-20 | 2012-11-15 | Lindi-Lee Kirkman / Francois Coetzee | (+27 )119286523 / ©825699852 / 116071281 | Lindik@atns.co.za / Francoisc@atns.co.za
No additional comments. MISSING FPL - Clocks - GPS Auto Sync. Transit times - within same min. Comm. links. On the whole stable. Challenges with hardware in customs when some VSAT equipment has challenges. Internal system delays - erroneous FPL queue in ATM system or incorrect addressed FPL. response TO MESSAGES - when messages are sent, responses are received. FAJS system auto responds to RQP and RQS messages received.
FBSK | BOTSWANA | yes | Ubitech | yes | 1-30 sep 2012 | 1-30 Sep 2012 | 2012-09-30 | 2012-10-01 | 2012-10-01 | yes | yes | Raytheon | same as AIM system | same as AIM system | same as AIM system | same as AIM system | same as AIM system | 2012-10-01 | 2012-11-15 | Samuel Mbaakanyi / Jobe Malefho | (+267) 368 8200 / (c)72277905 /(c) 71651176 | Smbaakanyi@caab.co.bw / JMalefho@caab.co.bw
Proposal expected from Raytheon / Ubitech on 14 May 2012 and expect to sign soon there after. Will send ICAO regional office update by 19 May 2012. MISSING FPL - task force formed. Clocks on GPS auto sync. Message switch clock is sometimes behind, timer stops running then manual intervention to restart. transit times delays, requires review. comm. links - local links on telecom, can be unreliable and take time to be restored. Internal system delays - messages queue at FDPS and must be manually manipulated or deleted. FMS stops running occasionally, system shows TX but still in queue for TX. FPL for following day only shows on position an hour before deep, so times out before the DEEP time. Botswana to provide ICAO regional office with report and plan to address the problems regarding missing FPL (9 June 2012).
FCBB | DRC
No in attendance
FDMS | SWAZILAND | no | VSAT - ATNS | YES | 2012-06-01 | 2012-06-01 | 2012-06-01 | 2012-06-01 | 2012-07-01 | no | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2012-10-01 | 2012-11-15 | Francis Kawoya / Nhlanhla Dube | (+268) 25184344 / ©76074828 / 76262182 | fkawoya@gmail.com / nhlanhla@swacaa.co.sz
No further comments. Missing FPL. Clocks synchronised manually with FAJS area control sector via telephone. Transit times - no noticeable difference. Comm. links - VSAT AVBL good. internal system delays occasionally due to manual faxing of FPL to ATC and distance that has to be walked.
FIMP | MAURITIUS | yes | Copperchase | yes | completed | completed | completed | 2012-06-01 | 2012-07-01 | yes | completed | THALES | completed | completed | completed | same as AIM system | same as AIM system | Currently | 2012-11-15 | Director CAA | (+230) 6032000 | civil-aviation@mail.gov.mu
Operational OJT on going. Awaiting to commence testing with other ANSP and airspace users as they become ready. Missing FPL. Transit times - no problems. Clock linked to ATC system GPS. FPL from Dubai with a 7 min time dif. Manual check also done DLY. issue with UAE flights from Dubai. Trend, for a few days at a time then ok for a while. lesser extent HAJJ flights from Jeddah no FPL. ICAO regional office to provide FIMM with feedback as to who are having challenges with FPL from FIMM.
FLLS | ZAMBIA | yes | Ubitech | yes(new) | 2012-07-01 | 2012-08-01 | 2012-09-01 | Aug/Sep 2012 | August/September 2012 | no | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2012-11-15 | Stanley Sitali / Jacqueline Malambo | (+260) 211271195 / © 977495215 / © 95282971 | stanley.sitali@lun.aero / jacqueline.malambo@lun.aero
Back up terminal for manual operations in the process of being acquired. Should be installed by end of June 2012. Missing FPL. Clock auto update with GPS. Old AFTN switch that is sometimes down. Replacement work is underway. Switch also linked to AIM system, but sometimes do not exchange info. Comm. link - local telecom unreliable on leased lines. moving to fibre optic and VPN internet several possible service providers. internal processes - standard operations, don't see DLA here. Service messages are automated, only problem when system is down.
FMMI | MADAGASCAR
Not in attendance
FNLU | ANGOLA
No updates on software delivery and testing
FQMA | MOZAMBIQUE | no | Copperchase | yes | 2012-06-30 | 2012-07-25 | 2012-07-30 | 2012-08-01 | 2012-08-01 | no | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2012-11-15 | Joana Agostinho / Dalilo A Amade | (c)(+258) 826516230 /© 828958570 | jomutimba@gmail.com / daliloamade@yahoo.com.br
No further comments. MISSING FPL - clocks - FQMA MANUAL CLOCKS VERIFIED AGAINST FQBR which has GPS clock. Transit times - within the same min. Links - VSAT to FAJS no main problems. Internal lines sometimes challenging moving to domestic VSAT with local telecom to improve reliability. internal system delays - RELATED TO NETWORK CHALLENGES. response to messages - NO ISSUES.
FSIA | SEYCHELLES
Information AVBL from the Kenya FCWM report
FVHA | ZIMBABWE | yes | Comsoft | yes | 2012-06-01 | 2012-06-01 | 2012-06-01 | 2012-06-01 | 2012-07-01 | yes | Radar system FDP decommissioned as of 15 Nov 2012 | n/a | n/a | n/a | n/a | n/a | n/a | 2012-08-01 | 2012-11-15 | Caleb Furawo / Erick Chavunduka | (+263) 4585006 / ©772422031 / © 712867855 | cfurawo@caaz.co.zw / erick@caaz.co.zw
Radar system upgrade/replacement due to take place from 2013. Current ATM Operations will use the Comsoft AMHS strip printers in the interim compliant to FPL 2012. MISSING FPL - clocks - auto GPS sync. Transit time - within the same min. Comm. Links - VPN network and VSAT network links reliable. internal SYSTEM DELAYS - none. Response to messages - manual response from queued messages.
FWLL | MALAWI | YES | Technobrain | yes | 2012-06-15 | 2012-07-01 | 2012-07-30 | 2012-08-01 | 2012-08-01 | yes | yes | Technobrain | same as AIM system | same as AIM system | same as AIM system | same as AIM system | same as AIM system | September/October 2012 | 2012-11-15 | Dixie Kwatani / MFT Bongwe | (+265) 888892494 / ©1770577 / 888867654 / © 1770577 | dkwatani@yahoo.co.uk / donchimtengo@yahoo.com
Will move in line with ATNS VSAT transmission dates. Full commitment from Government in support of this project received in March 2012. - missing FPL - CLOCKS AUTO SYNC WITH GPS. Transit time - no problem. Comm. links - leased lines reliable internal systems delays - NO ALARM TO ALER opr OF MESSAGES in queue, power system unreliable and can cause delays.response to messages - human attitude to responding to messages needs attention.
FXMM | LESOTHO | no | VSAT - ATNS | YES | 2012-06-01 | 2012-06-01 | 2012-06-01 | 2012-07-01 | 2012-09-01 | no | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2012-09-01 | 2012-11-15 | Ntsontso Joseph Molefi / Jacob Lesekele | (+266) 22350115 / © 58077517 / 22350362 / © 58489404 | jomolefi@graduate.org / jacoblesekele@hotmail.com
No further comments. Missing FPL - INTERNAL CLOCKS automatic sync with GPS. Transit delays - not experienced. Comm. links - STABLE /AVBL. INTERNAL SYSTEM DELAYS - none. QUERIES - no problems.
FYWH | NAMIBIA | no | Copperchase UK | yes | completed | completed | operational | 2012-06-01 | 2012-07-01 | yes | no | THALES / converter (Copperchase) | 2012-07-01 | 2012-07-01 | 2012-07-01 | 2012-07-01 | 2012-07-01 | 2012-08-01 | 2012-11-15 | Veronica Kandjabanga-Adeyeye / Hilma Leonard | (+264) 61702080 / © 812470437 / © 812455813 | adeyeyev@dca.com.na / caiso@dca.com.na
Installing a Copperchase converter between AFTN and Eurocat X. missing FPL. - clocks - auto sync GPS. Transit times - within the same min. Comm. Links - local telecoms lines some LAN some dial up and some on fibre. Internal system delays - none. Response to messages - no challenges. Namibia to send ICAO regional office a copy of procedures around missing FPL by end of May 2012.
FZAA | CONGO
Not in attendance
HBBA | BURUNDI | no | VSAT - ATNS | YES | 2012-06-01 | 2012-06-01 | 2012-06-01 | 2012-06-01 | 2012-07-01 | no | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2012-09-01 | 2012-11-15 | Diomede Ntawuhanakanka | (+257) 78818747 | diontawuhana@yahoo.fr
No further comments. Missing FPL. Clocks - auto sync with GPS. Will confirm this to ICAO regional office by 18 May 2012. Transit times - Kenya messages 14 mins out. Comm.. Links - VSAT to FAJS. Flight from East Congo do not have FPL. Internal sys delays - manual system. Response to messages - no issue.
HRYR | RWANDA
Not in attendance
HTDA | TANZANIA | yes | Egisavia | yes | 2012-05-01 | June/July 2012 | 2012-09-30 | Aug/Sep 2012 | August/September 2012 | yes | yes | Egisavia | same as AIS system | same as AIS system | same as AIS system | same as AIS system | same as AIS system | August/September 2012 | 2012-11-15 | Simon Kessy / Ali Chang'a | (+255) © 754403082 /© 755283680 | skessy@tcaa.go.tz / achanga2004@yahoo.co.uk
Challenge that there is no backup system for AFTN. Missing FPL: clock is GPS sync via network. Transit times are a few seconds time stamp is the same. Comm. links Telecomm company lines are unreliable and take long to repair. This contributes to delays in distribution to ATSU's. Telecomm company network infrastructure is vulnerable thus moving to fibre-optic lines. system generates an error with EOBT and ETD, FPL is rejected, this will be addressed with upgrade. Training/co-operation, Tanzania to inform ICAO regional office WI 7 days
Inter regional hub connections
YBBB | AUSTRALIA
LEEE | SPAIN
SAEZ | ARGENTINA
GOOO | SENEGAL
HKNA | KENYA
FCBB | GABON
Action Items for all states:
Provide training plan to ICAO
Keep ICAO informed re implementation status
Inform ICAO regarding contact person and details and keep them up to date
States to indicate to ICAO regional office that procedures around message handling are in place and are applicable and current and in use. 30 May 2012.
States to communicate by e-mail to the focal points what ATM/CNS systems are in use.
States to advise ICAO regional office and copy participants what IAIP (AIP, AMENDMENT, AIP SUP and AIC) do you have and when was last updated. By 30 May 2012.
VVIP flights - FPL are filed incorrectly (wrong DEP and times etc) FPL laps etc. this needs to be passed to the FPL TF and ask sub group for regional guidance.
As states are ready for testing they are to formally advise the applicable state via e-mail and formal test procedures will be agreed to with specific dates, times and conditions.
ICAO regional office to provide states with an AIC example re fell 2012. www.eurocontrol.int web page provides good guidance material (AIC and Training)
Missing flight plans common problems
Unsynchronised clocks
Delayed transit times
Communication links
Internal system delays
Lack of proper use of service message (RQP/RQS)
No response to query messages
Air Navigation Issues/challenges that impact on FPL -
Zambia - investment in the CNS/ATM infrastructure is challenging despite it being necessary with legacy systems. There is an investment plan in place for the next 5 years.
Swaziland - is currently disposing of legacy equipment that may be useful to other states. Interested states can approach Swaziland and discuss co-operation. It is suggested that on a regional bases we should be aware of who shares similar systems for possible co-operation.
Botswana - communication from ICAO regional office tends to be received late. ICAO informed that states (DG OFFICES) acknowledge receipt of the documents, however they do not seem to filter to the necessary, applicable persons. FPL 2012 focal points are also sent a copy of the invite.
Lesotho - there is a challenge around a requirement for more staff. Challenges around international travel approval and attendance of important meetings.
Malawi - attendance of meetings is not always the correct person( the one who does the job) and they do not train/pass on the information. Task is delegated to someone else who has to work from documentation.
Zimbabwe - lack of knowledge on new terms such as PBN etc… suggesting a new training module to address this challenge. Encourage engineering staff to interact without ICAO facilitation.
Mozambique - the AIS to AIM transmission, there needs to be more localised, sub regional workshops to improve understanding and address challenges
Namibia - applicable ICAO communication doesn’t seem to make it to the applicable people.
Burundi - training for staff is a challenge.
South Africa - the lack of on time aeronautical information
DAKAR FCWM GROUP
Tributary | State | Automated FPL system yes/no | System Vendor | will this be upgraded? | software implementation date | testing date | operational commissioning | ANSP testing date | users testing date | Automated ATM system yes/no | will this be upgraded? | System Vendor | software implementation date | testing date | operational commissioning | ANSP testing date | users testing date | Accepting FPL in new and present format date | Accepting FPL in NEW format only (15 NOV 2012?) | Operational contact person | tel / mobile | e-mail
| BENIN | PLANNED FOR 2013 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-07-26 | 2012-11-15
ADDITIONAL COMENTS: CLOCK: GPS TRANSIT TIMES: less than 1 min COMM LINKS: VSAT - ok CHALLENGES: none TRAINING: has commenced and will be on time
| BURKINA FASO | PLANNED FOR 2013 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | yes - strip printer | to be replaced by FDPS | tender | 2012-07-01 | 2012-07-01 | 2012-07-01 | 2012-07-01 | 2012-07-01 | 2012-07-26 | 2012-11-15
ADDITIONAL COMENTS: tender to replace strip printers with FDPS in 2013 CLOCK: GPS TRANSIT TIMES: within same min COMM LINKS: VSAT/AFISNET STABLE CHALLENGES: NONE TRAINING: COMMENCED, WILL BE READY
| CAMEROON | PLANNED FOR 2013 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | yes - strip printer | to be replaced by FDPS | tender | 2012-07-01 | 2012-07-01 | 2012-07-01 | 2012-07-01 | 1905-07-05 | 2012-07-26 | 2012-11-15 | Komguem Magni / Temfack Victor | (237) 33 429292 / 99 00 2550 / 99986160 / 99986160 | komguemmagniapo@asecna.org / victorfack@yahoo.fr / temfackvic@asecna.org
ADDITIONAL COMENTS: NONE CLOCK: GPS TRANSIT TIMES: WITHIN 1 MIN COMM LINKS: VSAT/AFISNET stable CHALLENGES: none TRAINING: commenced
| CENTRAL AFRICAN REPUBLIC | YES | COROBOR AFTN | YES | 2012-07-19 | 2012-07-20 | 2012-07-26 | 2012-07-27 | 2012-07-26 | NO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-07-26 | 2012-11-01 | ZOUNGARANI Liliane / KIAPO Alexandre | 23675504943 / 236 75752598 | centytess@yaho.fr / akiaps@yahoo.fr
ADDITIONAL COMENTS: NONE CLOCK: GPS TRANSIT TIMES: WITHIN SAME MIN COMM LINKS: VSAT STABLE CHALLENGES: NONE TRAINING: COMMENCED
| CHAD | YES | COROBOR AFTN | YES | 2012-07-19 | 2012-07-20 | 2012-07-26 | 2012-07-27 | 2012-07-26 | YES | Thales (strip printer) | 2012-04-12 | 2012-04-01 | 2012-04-01 | 2012-04-01 | n/a | n/a | 2012-07-26 | 2012-11-15 | Bemadjibaye Alkader / Dovonucopdi Gustave | (235) 90148268 | bemadjibayealk@asecna.org
ADDITIONAL COMENTS: none CLOCK: GPS TRANSIT TIMES: wi same min COMM LINKS: vsat CHALLENGES: none TRAINING: in progress
No information on progress | DEM REP OF CONGO
NO INFO AVBL. ADDITIONAL COMENTS: CLOCK: TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
| COTE D'IVOIRE | YES | COROBOR AFTN | YES | 2012-07-19 | 2012-07-20 | 2012-07-26 | 2012-07-27 | 2012-07-26 | YES | Thales (strip printer) | 2012-04-12 | 2012-04-01 | 2012-04-01 | 2012-04-01 | n/a | n/a | 2012-07-26 | 2012-11-15
ADDITIONAL COMENTS: CLOCK: TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
| GABON | YES | COROBOR AFTN | YES | 2012-07-19 | 2012-07-20 | 2012-07-26 | 2012-07-27 | 2012-07-26 | NO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-07-26 | 2012-11-15 | Lindzondzo Balembou Amelina | (+241) 05 182262 | mbouroubalem@yahoo.fr / lindzondzobalembouame@asecna.org
ADDITIONAL COMENTS: CLOCK: TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
| GUINEA EQUATORIALE | YES | COROBOR AFTN | YES | 2012-07-19 | 2012-07-20 | 2012-07-26 | 2012-07-27 | 2012-07-26 | no | N/A | n/a | n/a | n/a | n/a | n/a | n/a | 2012-07-26 | 2012-11-15 | Mbulu Obiang Vivgilio / Gil Esopi Bolekia | (+240)222 792150 / 273944 | MBULUOBIANGVir@asecna.org/GUINEEEQCHEFENA@asecna.org
ADDITIONAL COMENTS: none CLOCK: GPS TRANSIT TIMES: COMM LINKS: none CHALLENGES: none TRAINING: 15 June 2012
| LIBERIA | NO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-07-01 | 2012-11-15
ADDITIONAL COMENTS: CLOCK: GPS TRANSIT TIMES: LESS THAN 1 MIN COMM LINKS: VSAT stable CHALLENGES: none TRAINING: done
ASECNA to provide updates | MADAGASCAR | YES | SAGEM AFTN | YES | 2012-07-19 | 2012-07-20 | 2012-07-26 | 2012-07-27 | 2012-07-26 | YES | Thales (strip printer) | 2012-04-12 | 2012-04-01 | 2012-04-01 | 2012-04-01 | n/a | n/a | 2012-07-26 | 2012-11-15 | ANDRIQNIERENANA NARY | (+261) 332337034 | ANDRIANIERENANANAR@ASECNA.ORG
ADDITIONAL COMENTS: CLOCK: TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
| MALI | PLANNED FOR 2013 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | yes - strip printer | to be replaced by FDPS | tender | 1905-07-05 | 1905-07-05 | 1905-07-05 | 1905-07-05 | 1905-07-05 | 2012-07-26 | 2012-11-15
ADDITIONAL COMENTS: CLOCK: TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
| MAURITANIA | PLANNED FOR 2013 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | yes - strip printer | to be replaced by FDPS | tender | 1905-07-05 | 1905-07-05 | 1905-07-05 | 1905-07-05 | 1905-07-05 | 2012-07-26 | 2012-11-15
ADDITIONAL COMENTS: CLOCK: TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
| NIGER | YES | COROBOR AFTN | YES | 2012-07-19 | 2012-07-20 | 2012-07-26 | 2012-07-27 | 2012-07-26 | YES | Thales (strip printer) | 2012-04-12 | 2012-04-01 | 2012-04-01 | 2012-04-01 | n/a | n/a | 2012-07-26 | 2012-11-15
ADDITIONAL COMENTS: CLOCK: TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
| ROBERTS FIR | YES | intelcan | yes | completed | completed | completed | 2012-07-26 | 2-5 Aug 2012 | yes | same as AIM | completed | completed | completed | same as AIM system | same as AIM system | same as AIM system | 2012-07-01 | 2012-11-15 | Buya Mansaray / Philip B Trye | (231) 886974149 / 886887160 | bsmansaray9@gmail.com / bobsonjr2004@yahoo.com
ADDITIONAL COMENTS: CLOCK: GPS TRANSIT TIMES: LESS THAN 1 MIN COMM LINKS: VSAT stable CHALLENGES: none TRAINING: done
| SENEGAL | YES | COROBOR AFTN | YES | 2012-07-19 | 2012-07-20 | 2012-07-26 | 2012-07-27 | 2012-07-26 | YES | Thales (strip printer) | 2012-04-12 | 2012-04-01 | 2012-04-01 | 2012-04-01 | n/a | n/a | 2012-07-26 | 2012-11-15
ADDITIONAL COMENTS: none CLOCK: GPS TRANSIT TIMES: wi same min COMM LINKS: vsat CHALLENGES: none TRAINING: in progress
| TOGO | PLANNED FOR 2013 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-07-26 | 2012-11-15
ADDITIONAL COMENTS: CLOCK: GPS TRANSIT TIMES: less than 1 min COMM LINKS: VSAT - ok CHALLENGES: none TRAINING: has commenced and will be on time
ASECNA to provide updates | UNION DES COMORES | YES | COROBOR AFTN | YES | 2012-07-19 | 2012-07-20 | 2012-07-26 | 2012-07-27 | 2012-07-26 | YES | Thales (strip printer) | 2012-04-12 | 2012-04-01 | 2012-04-01 | 2012-04-01 | n/a | n/a | 2012-07-26 | 2012-11-15 | SOULE Omar | (+269) 323 32 23 | SOULEOma@asecna.org
ADDITIONAL COMENTS: CLOCK: GPS TRANSIT TIMES: less than 1 min COMM LINKS: VSAT - ok CHALLENGES: none TRAINING: has commenced and will be on time
| CAPE VERDE | YES | INDRA | YES | 2012-05-30 | 2012-06-01 | 2012-09-26 | jul and Aug 2012 | Jul and Aug 2012 | yes | YES | INDRA | same as AIM system | same as AIM system | same as AIM system | same as AIM system | same as AIM system | 2012-09-01 | 2012-11-15 | Aristides Martins / Jose Carlos Fernandes | (238) 24 12090 / 99 15602 / 2419200 | tidesmartins@gmail.com / jcarlos@asa.cv
ADDITIONAL COMENTS: CLOCK: GPS TRANSIT TIMES: within same min COMM LINKS: VSAT stable CHALLENGES: none TRAINING: planned for Sep and Oct 2012
| CONGO | yes | COROBOR AFTN | YES | 2012-07-19 | 2012-07-20 | 2012-07-26 | 2012-07-27 | 2012-07-26 | YES | Thales (strip printer) | 2012-04-12 | 2012-04-01 | 2012-04-01 | 2012-04-01 | n/a | n/a | 2012-07-26 | 2012-11-15 | mabiala Gral Quiji / Goita Issa Salif | +242 06 9920474 / 9920454 | mabialambabiagla@asecna.org / goitaiss@ascena.org
ADDITIONAL COMENTS: none CLOCK: GPS TRANSIT TIMES: within the 5 min COMM LINKS: links btn Brazzaville and Kinshasa link obsolete and in discussions to get new. and Brazaville and Luanda not operational.SADC VSAT hardware problems. CHALLENGES: none TRAINING: from 15 June 2012
| GHANA | YES | Copper chase CHG to Comsoft | replacement | May/jun 2012 | 2012-07-01 | 2012-07-01 | 2012-07-07 | 2012-07-01 | YES | Alenia Marconi | yes | 2012-07-02 | 2012-07-01 | 2012-07-01 | 2012-07-01 | 2012-07-01 | 2012-07-01 | 2012-11-15 | Dan Mensah / Sadiq Osman | (233) 244635453 / 243188108 | danmensa@yahoo.com / sadeeisco@yahoo.com
ADDITIONAL COMENTS: none CLOCK: GPS TRANSIT TIMES: 1 MIN COMM LINKS: VSAT INTERMITTED CHALLENGES: INTERMITTENT COMM LINKS, NO SPAIRS, planned replacement. State to provide information regarding replacment plans to ICAO by end of May 2012 TRAINING: on going
| GUINEA BISSAU | YES | COROBOR AFTN | YES | 2012-07-19 | 2012-07-20 | 2012-07-26 | 2012-07-27 | 2012-07-26 | no | N/A | n/a | n/a | n/a | n/a | n/a | n/a | 2012-07-26 | 2012-11-15
ADDITIONAL COMENTS: CLOCK: TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
| KENYA | YES | EGISAVIA | YES | 2012-05-24 | 2012-07-01 | 2012-07-01 | 2012-07-01 | 2012-07-01 | yes | yes | Thales Eurocat | 2012-08-01 | 2012-08-01 | 2012-08-01 | 2012-08-01 | 2012-08-01 | 2012-07-01 | 2012-11-15 | Maina | 254721493957 | jkmaina@kcaa.or.ke
ADDITIONAL COMENTS: none CLOCK: GPS (manual) TRANSIT TIMES: 1 min COMM LINKS: stable VSAT CHALLENGES: none TRAINING: started
| MOROCCO | yes | INDRA | yes | JUNE 2012 | 10-15 JUNE | 15 JUNE | JULY | 1 July 2012-14 November 2012 | YES | YES | INDRA | same as AIM system | same as AIM system | same as AIM system | same as AIM system | same as AIM system | 2012-10-15 | 2012-11-15 | KAITER/JAMAL EL ASSAL MOHAMMED | 212660100051/212660100062 | j.kaiter@onda.ma m.elassal@onda.ma
ADDITIONAL COMENTS: CLOCK: TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
| GUINEA CONAKRY | NO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-07-01 | 2012-11-15 | Mamadou Saliou Diallo | (224)64776382 / 68981747 | saliou2ana@yahoo.fr
ADDITIONAL COMENTS: CLOCK: GPS TRANSIT TIMES: LESS THAN 1 MIN COMM LINKS: VSAT stable CHALLENGES: none TRAINING: done
| SIERRA LEONE | NO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-07-01 | 2012-11-15
ADDITIONAL COMENTS: CLOCK: GPS TRANSIT TIMES: LESS THAN 1 MIN COMM LINKS: VSAT stable CHALLENGES: none TRAINING: done
ADDITIONAL COMENTS: CLOCK: GPS TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
| ANGOLA | YES | COMSOFT AMHS | YES | 2012-04-25 | 2012-04-30 | 2012-06-01 | 2012-06-01 | 2012-06-01 | no | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2012-07-01 | 2012-11-15 | Marcelina Sapalo | +244923501927 | msapalo@enana-ao.com
ADDITIONAL COMENTS: none CLOCK: GPS TRANSIT TIMES: 2 MIN COMM LINKS: reliable CHALLENGES: would like to impliment a domestic VSAT network. TRAINING: completed
| NIGERIA | no | on tender | yes | aug/sep 2012 | 2012-10-01 | 2012-10-01 | 2012-10-01 | 2012-10-01 | yes | yes | Thales Eurocat | 2012-08-01 | 2012-08-01 | 2012-09-01 | 2012-09-01 | 2012-09-01 | 2012-10-01 | 2012-11-15 | Nwamkwo Ifeamyi Francis / Olajire Aderemi / Matthew Lawrence Pwajok | (234) 8034710708 / 1 8776675 / 8034531431 / 8024797711 / 8050786333 | ifnwankwo@yahoo.com / aaolajire@yahoo.co.uk / pwajokmathewlawrence@yahoo.com
ADDITIONAL COMENTS: none CLOCK: GPS TRANSIT TIMES: LESS THAN 1 MIN COMM LINKS: AFISNET / VSAT stable CHALLENGES: unreliable power. Deploying UPS and solar systems TRAINING: commenced and on going remaining outstanding to be completed Jun/Jul 2012
FAJS | SOUTH AFRICA | Yes | THALES | yes | 2012-06-01 | 1-6 June 2012 | 2012-06-06 | 7-30 June 2012 | 1 July 2012-14 November 2012 | yes | yes | THALES | same as AIM system | same as AIM system | same as AIM system | same as AIM system | same as AIM system | 2012-09-20 | 2012-11-15 | Lindi-Lee Kirkman / Francois Coetzee | (+27 )119286523 / ©825699852 / 116071281 | Lindik@atns.co.za / Francoisc@atns.co.za
ADDITIONAL COMMENTS: no additional comments. CLOCK: GPS Auto Sync. TRANSIT TIMES: within same min. COMM LINK: On the whole stable. CHALLENGES: with hardware in customs when some VSAT equipment has challenges. Internal system delays - erroneous FPL queue in ATM system or incorrect addressed FPL. response TO MESSAGES - when messages are sent, responses are received. FAJS system auto responds to RQP and RQS messages received.
NOT PRESENT | ALGERIA
NO INFO AVBL. ADDITIONAL COMENTS: CLOCK: TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
NOT PRESENT | GAMBIA
NO INFO AVBL. ADDITIONAL COMENTS: CLOCK: TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
ISSUES TO ADDRESS
interface Dakar Recife and Dakar Laspalmas
interface Niamey / Algers and Niamey/Adis
Missing FPL
states that interact with IFPS should participate with the IFPS testing
Nigeria will get back to ATNS on the missing ARIK Air FPL
a key factor could be incorrect AFTN addressing - states should check and verify addresses
check clocks
check transit times
check internal system delays
check links
procedures for message handeling, review and improve or impliment
airlines need to update their address systems
actions
procedures developer: Nigeria, ASECNA, KENYA first draft by end of first week of June and complete work by first week of July. Co-ordinator Nigeria
Air Nav implimentation issues
sesitise the regulator to inform the airlines that they require training too
any other business
include regional officer AIM in documents for circulation
update of FITS
publication date of AIC - ICAO AIMO
apeal to states not to impliment anyother major changes on 15 November 2012
ADDIS ABABA FCWM GROUP
Tributary | State | Automated FPL system yes/no | System Vendor | will this be upgraded? | software implementation date | testing date | operational commissioning | ANSP testing date | users testing date | Automated ATM system yes/no | will this be upgraded? | System Vendor | software implementation date | testing date | operational commissioning | ANSP testing date | users testing date | Accepting FPL in new and present format date | Accepting FPL in NEW format only (15 NOV 2012?) | Operational contact person | tel / mobile | e-mail
No information on software delivery and testing/progress | DJIBOUTI
ADDITIONAL COMENTS: CLOCK: GPS TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
No information on software delivery and testing/progress | ERITREA
ADDITIONAL COMENTS: CLOCK: GPS TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
ETHIOPIA
ADDITIONAL COMENTS: CLOCK: GPS TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
RWANDA
ADDITIONAL COMENTS: CLOCK: GPS TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
SAUDI ARABIA
ADDITIONAL COMENTS: CLOCK: GPS TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
SUDAN
ADDITIONAL COMENTS: CLOCK: GPS TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
No updates on software delivery & testing | SOUTH SUDAN
ADDITIONAL COMENTS: CLOCK: GPS TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
NAIROBI FCWM GROUP
NAIROBI GROUP
Tributary | State | Automated FPL system yes/no | System Vendor | will this be upgraded? | software implementation date | testing date | operational commissioning | ANSP testing date | users testing date | Automated ATM system yes/no | will this be upgraded? | System Vendor | software implementation date | testing date | operational commissioning | ANSP testing date | users testing date | Accepting FPL in new and present format date | Accepting FPL in NEW format only (15 NOV 2012?) | Operational contact person | tel / mobile | e-mail
| KENYA | Yes | Egisavia | Yes | July 18th 2012 | July 18th 2012 | July 18th 2012 | Sept 24th 2012 | Oct 3rd 2012 | Yes | Yes | Egisavia | July 18th 2012 | July 18th 2012 | July 18th 2012 | Sept 24th 2012 | Oct 3rd 2012 | Sept 20th 2012 | Nov 15th 2012 | Joseph k maina | 254 721 493 957 | jkmaina@kcaa.or.ke
ADDITIONAL COMENTS: CLOCK: GPS -GPS clock available not synchronized with system clock. TRANSIT TIMES: 2 min COMM LINKS: Adequate CHALLENGES: Workload in converting FPL and related Mssg for neighbouring FIRs TRAINING: On-going
MADAGASCAR
ADDITIONAL COMENTS: CLOCK: GPS TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
MAURITIUS
ADDITIONAL COMENTS: CLOCK: GPS TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
MORONI
ADDITIONAL COMENTS: CLOCK: GPS TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
| SEYCHELLES | Yes | Indra-Systema | Yes | June 1st 2012 | June 15th 2012 | June 15th 2012 | July 2012 | July-Nov 2012 | Yes | Yes | Indra-Systema | June 1st 2012 | June 1st 2012 | June 1st 2012 | July 1st 2012 | July-Nov 2012 | Sept 20th 2012 | Nov 15th 2012 | Esmee Samson | 248 252 720 6 | esamson@scaa.sc
ADDITIONAL COMENTS: CLOCK: GPS OK TRANSIT TIMES: OK COMM LINKS: OK CHALLENGES: NIL TRAINING: Completed
| SOMALIA | No | No | No | N/A | N/A | N/A | N/A | June 2012 | No | No | N/A | N/A | N/A | N/A | N/A | No | 14/05/2012 | Nov 15th 2012 | Humphrey K. Mwachoki | 254 20 762 2785 | humphrey.mwachoki@icao.unon.org
ADDITIONAL COMENTS: CLOCK: GPS No TRANSIT TIMES: Ok COMM LINKS: OK CHALLENGES: Origination of flight plans TRAINING: On-going
Late delivery of software | TANZANIA | Yes | Egisavia | Yes | Oct 22nd 2012 | Oct 27th 2012 | Oct 26th 2012 | Nov 3rd 2012 | Nov 7th 2012 | Yes | Yes | Egisavia | Oct 22nd 2012 | Oct 27th 2012 | Oct 26th 2012 | Nov 3rd 2012 | Nov 7th 2012 | Sept 17th 2012 | Nov 15th 2012 | Deo Mushi | 255 713 429 253 | dmushi@tcaa.go.tz
ADDITIONAL COMENTS: CLOCK: GPS Available not connected TRANSIT TIMES: 4min COMM LINKS: Ok CHALLENGES: Link with domestic airports TRAINING: On-going
Late delivery of software | UGANDA | Yes | Indra-Systema | Yes | Oct 25th 2012 | Oct 25th 2012 | Oct 31st 2012 | Oct 26- 30 2012 | Oct 25th 2012 | Yes | Yes | Indra-Systema | 22/10/2012 | Oct 25th 2012 | Oct 31st 2012 | Oct 27-30 2012 |  | Sept 20th 2012 | Nov 15th 2012 | Aloysius Mulekezi | 256 777 210 891 | amulekezi@caa.co.ug
ADDITIONAL COMENTS: CLOCK: GPS OK TRANSIT TIMES: 15 min COMM LINKS: OK CHALLENGES: No automatic connection and distribution internally TRAINING: on-goin
Late delivery of software | Eritrea | No | Copperchase | No | Oct 29th 2012 | Nov 3rd 2012 | Oct 30th 2012 | Oct 30th 2012 | Nov 1st-7th 2012 | No | No | N/A | N/A | N/A | N/A | Nov 1st-7th 2012 | Nov 1st-7th 2012 | Nov 11th 2012 | Nov 15th 2012 | Mesfin Berhane | 291 1 18 1424 | mesfin.berhane6@gmail.com
ADDITIONAL COMENTS: CLOCK: GPS Ok TRANSIT TIMES: OK COMM LINKS: OK CHALLENGES: Nil TRAINING: On-going
| Ethiopia | Yes | Radiocom | Yes | Feb 2nd 2012 | April 1st 2012 | April 1st 2012 | June 1st 2012 | July 1st 2012 | Yes | Yes | Selex | Nov 1st 2011 | April 1st 2012 | April 1st 2012 | June 1st 2012 | July 1st 2012 | June 30th 2012 | Nov 15th 2012 | Shimeles Kibreab | 251 911 201 267 | shimeleskibreab@gmail.com
ADDITIONAL COMENTS: CLOCK: GPS Ok TRANSIT TIMES: OK COMM LINKS: OK CHALLENGES: Nil flight plans for aircraft from Mogadishu FIR TRAINING: Complete
Late delivery of software | South Sudan | No | TDN | Yes | Before Nov 15th 2012 | Before Nov 15th 2012 | Before Oct 31st 2012 | TBN | TBN | No | Yes | TBN | Before Nov 15th 2012 | TBN | TBN | TBN | TBN | Oct 15th 2012 | Nov 15th 2012 | Martin L'onga David | 211 956 922 369 | Kenyiadeba@yahoo.com
ADDITIONAL COMENTS: CLOCK: GPS No TRANSIT TIMES: Nil comm COMM LINKS: Nil CHALLENGES: Training of personnel TRAINING: On-going