## Sheet1
ASECNA GROUP
Tributary | State | Automated FPL system yes/no | System Vendor | will this be upgraded? | software implementation date | testing date | operational commissioning | ANSP testing date | users testing date | Automated ATM system yes/no | will this be upgraded? | System Vendor | software implementation date | testing date | operational commissioning | ANSP testing date | users testing date | Accepting FPL in new and present format date | Accepting FPL in NEW format only (15 NOV 2012?) | Operational contact person | tel / mobile | e-mail
| BENIN | PLANNED FOR 2013 | THALES/COROBOR | YES | COROBOR 2011 | FROM 26/07 | YES | FROM 26/07 | NOT YET | NO | YES | Thales Eurocat | 2013 | N/A | N/A | N/A | N/A | 2012-07-26 | 2012-11-15 | Dovonou Vivien |  | beninena@asecna.org
µ
| BURKINA FASO | PLANNED FOR 2013 | THALES/COROBOR | YES | COROBOR 2011 | FROM 26/07 | YES | FROM 26/07 | NOT YET | yes - strip printer | to be replaced by FDPS | tender | 2012-07-01 | 2012-07-01 | 2012-07-01 | 2012-07-01 | 2012-07-01 | 2012-07-26 | 2012-11-15 | Ouedraogo Fulgence |  | burkinaena@asecna.org
ADDITIONAL COMENTS: tender to replace strip printers with FDPS in 2013 CLOCK: GPS TRANSIT TIMES: within same min COMM LINKS: VSAT/AFISNET STABLE CHALLENGES: NONE TRAINING: COMMENCED, WILL BE READY
| CAMEROON | PLANNED FOR 2013 | THALES/COROBOR | YES | COROBOR 2011 | FROM 26/07 | YES | FROM 26/07 | NOT YET | yes - strip printer | to be replaced by FDPS | tender | 2012-07-01 | 2012-07-01 | 2012-07-01 | 2012-07-01 | 2012-07-12 | 2012-07-26 | 2012-11-15 | Komguem Magni / Temfack Victor | (237) 33 429292 / 99 00 2550 / 99986160 / 99986160 | komguemmagniapo@asecna.org / victorfack@yahoo.fr / temfackvic@asecna.org
ADDITIONAL COMENTS: NONE CLOCK: GPS TRANSIT TIMES: WITHIN 1 MIN COMM LINKS: VSAT/AFISNET stable CHALLENGES: none TRAINING: commenced
| CENTRAL AFRICAN REPUBLIC | YES | THALES/COROBOR | YES | COROBOR 2011 | FROM 26/07 | YES | FROM 26/07 | NOT YET | YES-STRIP PRINTER | to be replaced by FDPS | TENDER | 2012-07-12 | 2012-07-12 | 2012-07-12 | 2012-07-12 | 2012-07-12 | 2012-07-26 | 2012-11-01 | ZOUNGARANI Liliane / KIAPO Alexandre | 23675504943 / 236 75752598 | centytess@yaho.fr / akiaps@yahoo.fr
ADDITIONAL COMENTS: NONE CLOCK: GPS TRANSIT TIMES: WITHIN SAME MIN COMM LINKS: VSAT STABLE CHALLENGES: NONE TRAINING: COMMENCED
| CHAD | YES | THALES/COROBOR | YES | 1905-06-27 | 2012-07-20 | YES | 2012-07-27 | 2012-07-26 | YES | 17/08/12 | Thales Eurocat | 2012-04-01 | 2012-07-01 | N/A | 2012-07-01 | n/a | 2012-07-26 | 2012-11-15 | Bemadjibaye Alkader / Dovonou Gustave | (235) 90148268 | bemadjibayealk@asecna.org
ADDITIONAL COMENTS: none CLOCK: GPS TRANSIT TIMES: wi same min COMM LINKS: vsat CHALLENGES: none TRAINING: in progress
No information on progress | DEM REP OF CONGO
NO INFO AVBL. ADDITIONAL COMENTS: CLOCK: TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
| COTE D'IVOIRE | YES | THALES/COROBOR | YES | 31/07/2012 | 2012-07-20 | YES | 2012-07-27 | 2012-07-26 | YES | Thales (strip printer) | 2012-04-12 | 2012-04-01 | 2012-04-01 | 2012-04-01 | 2012-07-01 | n/a | 2012-07-26 | 2012-11-15 | Kamgua Charles |  | ivoireena@asecna.org
ADDITIONAL COMENTS: CLOCK: TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
| GABON | YES | THALES/COROBOR | YES | 2012-07-19 | 2011-06-01 | YES | 2012-07-27 | 2012-07-26 | PLANNED FOR 2013 | YES | Thales Eurocat | 2013 | N/A | N/A | N/A | N/A | 2012-07-26 | 2012-11-15 | Kowet Emmanuel | (+241) 05 182262 | mbouroubalem@yahoo.fr / lindzondzobalembouame@asecna.org
ADDITIONAL COMENTS: CLOCK: TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
| GUINEA EQUATORIALE | YES | THALES/COROBOR | YES | 2012-07-19 | 2012-07-20 | YES | 2012-07-27 | 2012-07-26 | PLANNED FOR 2013 | N/A | Thales Eurocat | 2013 | n/a | n/a | n/a | n/a | 2012-07-26 | 2012-11-15 | Mbulu Obiang Vivgilio / Gil Esopi Bolekia | (+240)222 792150 / 273944 | MBULUOBIANGVir@asecna.org/GUINEEEQCHEFENA@asecna.org
ADDITIONAL COMENTS: none CLOCK: GPS TRANSIT TIMES: COMM LINKS: none CHALLENGES: none TRAINING: 15 June 2012
| LIBERIA | YES | intelcan | NO | 15/03/2012 | 2012-06-01 | 2012-04-01 | 26/07/2012 | 26/07/2012 | NO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-07-01 | 2012-11-15 | MARCUS ENDERS | (+231) 886 825 835 | mkenders@liberiacaa.com
ADDITIONAL COMENTS: CLOCK: GPS TRANSIT TIMES: LESS THAN 1 MIN COMM LINKS: VSAT stable CHALLENGES: none TRAINING: done
ASECNA to provide updates | MADAGASCAR | YES | SAGEM AFTN | YES | 2012-07-19 | 2012-07-20 | YES | 2012-07-27 | 2012-07-26 | YES | YES | Thales Eurocat | 20/07/2012 | 2012-07-01 | N/A | 2012-07-01 | 2012-07-01 | 2012-07-26 | 2012-11-15 | ANDRIQNIERENANA NARY | (+261) 332337034 | ANDRIANIERENANANAR@ASECNA.ORG
ADDITIONAL COMENTS: CLOCK: TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
| MALI | PLANNED FOR 2013 | N/A | N/A | N/A | N/A | YES | N/A | N/A | yes - strip printer | to be replaced by FDPS | Thales Eurocat | NEXT YEAR | NEXT YEAR | N/A | N/A | N/A | 2012-07-26 | 2012-11-15 | Berthe Adama |  | maliena@asecna.org
ADDITIONAL COMENTS: CLOCK: TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
| MAURITANIA | PLANNED FOR 2013 | N/A | N/A | N/A | N/A | YES | N/A | N/A | yes - strip printer | to be replaced by FDPS | Thales Eurocat | NEXT YEAR | NEXT YEAR | N/A | N/A | N/A | 2012-07-26 | 2012-11-15 | Gakou Abdel Kader |  | mauritanieena@asecna.org
ADDITIONAL COMENTS: CLOCK: TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
| NIGER | YES | COROBOR AFTN | YES | 2012-07-19 | 2012-07-20 | YES | 2012-07-27 | 2012-07-26 | YES | YES | Thales Eurocat | 31/5/2010 | 2012-06-01 | YES | 2012-07-01 | n/a | 2012-07-26 | 2012-11-15 | Ali Sayabou |  | nigerena@asecna.org
ADDITIONAL COMENTS: CLOCK: TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
| ROBERTS FIR | YES | intelcan | NO | 15/03/2012 | 2012-06-01 | 2012-04-01 | 26/07/2012 | 26/07/2012 | YES | YES | INTELCOM | PLANNED 2012 | N/A | N/A | N/A | N/A | 2012-07-01 | 2012-11-15 | Buya Mansaray / Philip B Trye | (231) 886974149 / 886887160 | bsmansaray9@gmail.com / bobsonjr2004@yahoo.com
ADDITIONAL COMENTS: CLOCK: GPS TRANSIT TIMES: LESS THAN 1 MIN COMM LINKS: VSAT stable CHALLENGES: none TRAINING: done
| SENEGAL | YES | COROBOR AFTN | YES | 2012-07-19 | 2012-07-20 | YES | 2012-07-27 | 2012-07-26 | YES | FDPS | Thales Eurocat | 20/4/2006 | 2012-04-01 | YES | 2012-07-01 | n/a | 2012-07-26 | 2012-11-15 | Basse Diaga |  | senegalena@asecna.org
ADDITIONAL COMENTS: none CLOCK: GPS TRANSIT TIMES: wi same min COMM LINKS: vsat CHALLENGES: none TRAINING: in progress
| TOGO | YES | COROBOR AFTN | YES | 15/07/2012 | 2012-07-01 | YES | 2012-07-01 | N/A | PLANNED FOR 2013 | FDPS | Thales Eurocat | 2013 | N/A | NO | N/A | N/A | 2012-07-26 | 2012-11-15 | Atisso Komlan |  | togoena@asecna.org
ADDITIONAL COMENTS: CLOCK: GPS TRANSIT TIMES: less than 1 min COMM LINKS: VSAT - ok CHALLENGES: none TRAINING: has commenced and will be on time
ASECNA to provide updates | UNION DES COMORES | YES | COROBOR AFTN | YES | 15/07/2012 | 2012-07-01 | YES | 2012-07-01 | N/A | PLANNED FOR 2013 | FDPS | Thales Eurocat | 2013 | N/A | NO | N/A | N/A | 2012-07-26 | 2012-11-15 | Mawule Atikpo Ayayi | (+269) 323 32 23 | comoresena@asecna.org
ADDITIONAL COMENTS: CLOCK: GPS TRANSIT TIMES: less than 1 min COMM LINKS: VSAT - ok CHALLENGES: none TRAINING: has commenced and will be on time
| CAPE VERDE | YES | INDRA | YES | 15/10/2012 | 26/10/2012 | 26/10/2012 | 26/10/2012 | Jul and Aug 2012 | yes | YES | INDRA | 15/10/2012 | same as AIM system | same as AIM system | same as AIM system | same as AIM system | 2012-09-01 | 2012-11-15 | Aristides Martins / Jose Carlos Fernandes | (238) 24 12090 / 99 15602 / 2419200 | tidesmartins@gmail.com / jcarlos@asa.cv
ADDITIONAL COMENTS: CLOCK: GPS TRANSIT TIMES: within same min COMM LINKS: VSAT stable CHALLENGES: none TRAINING: planned for Sep and Oct 2012
| CONGO | yes | COROBOR AFTN | YES | 2012-07-19 | 2012-07-20 | YES | 2012-07-27 | 2012-07-26 | YES | FDPS | Thales Eurocat | 13/4/2012 | 2012-04-01 | 30/4/2012 | 2012-07-01 | n/a | 2012-07-26 | 2012-11-15 | mabiala Gral Quiji / Goita Issa Salif | +242 06 9920474 / 9920454 | mabialambabiagla@asecna.org / goitaiss@ascena.org
ADDITIONAL COMENTS: none CLOCK: GPS TRANSIT TIMES: within the 5 min COMM LINKS: links btn Brazzaville and Kinshasa link obsolete and in discussions to get new. and Brazaville and Luanda not operational.SADC VSAT hardware problems. CHALLENGES: none TRAINING: from 15 June 2012
| GHANA | YES | Copper chase CHG to Comsoft | replacement | May/jun 2012 | 2012-07-01 | 2012-07-01 | 2012-07-07 | 2012-07-01 | YES | Alenia Marconi | yes | 2012-07-02 | 2012-07-01 | 2012-07-01 | 2012-07-01 | 2012-07-01 | 2012-07-01 | 2012-11-15 | Dan Mensah / Sadiq Osman | (233) 244635453 / 243188108 | danmensa@yahoo.com / sadeeisco@yahoo.com
ADDITIONAL COMENTS: none CLOCK: GPS TRANSIT TIMES: 1 MIN COMM LINKS: VSAT INTERMITTED CHALLENGES: INTERMITTENT COMM LINKS, NO SPAIRS, planned replacement. State to provide information regarding replacment plans to ICAO by end of May 2012 TRAINING: on going
| GUINEA BISSAU | YES | COROBOR AFTN | YES | 2012-07-19 | 2012-07-20 | 2012-07-26 | 2012-07-27 | 2012-07-26 | PLANNED 2013 | YES | Thales Eurocat | 2013 | n/a | n/a | n/a | n/a | 2012-07-26 | 2012-11-15 | Nadjitessem Gaou |  | bissauena@asecna.org
ADDITIONAL COMENTS: CLOCK: TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
| KENYA | YES | EGISAVIA | YES | 2012-05-24 | 2012-07-01 | 2012-07-01 | 2012-07-01 | 2012-07-01 | yes | yes | Thales Eurocat | 2012-08-01 | 2012-08-01 | 2012-08-01 | 2012-08-01 | 2012-08-01 | 2012-07-01 | 2012-11-15 | Maina | 254721493957 | jkmaina@kcaa.or.ke
ADDITIONAL COMENTS: none CLOCK: GPS (manual) TRANSIT TIMES: 1 min COMM LINKS: stable VSAT CHALLENGES: none TRAINING: started
| MOROCCO | yes | INDRA | yes | JUNE 2012 | 10-15 JUNE | 15 JUNE | JULY | 1 July 2012-14 November 2012 | YES | YES | INDRA | same as AIM system | same as AIM system | same as AIM system | same as AIM system | same as AIM system | 2012-10-15 | 2012-11-15 | KAITER/JAMAL EL ASSAL MOHAMMED | 212660100051/212660100062 | j.kaiter@onda.ma m.elassal@onda.ma
ADDITIONAL COMENTS: CLOCK: TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
| GUINEA CONAKRY | YES | intelcan | NO | 15/03/2012 | 2012-06-01 | 2012-04-01 | 26/07/2012 | 26/07/2012 | NO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-07-01 | 2012-11-15 | Saliou Diallo | (+224) 64776382 | saliou2@yahoo.fr
ADDITIONAL COMENTS: CLOCK: GPS TRANSIT TIMES: LESS THAN 1 MIN COMM LINKS: VSAT stable CHALLENGES: none TRAINING: done
| SIERRA LEONE | YES | intelcan | NO | 15/03/2012 | 2012-06-01 | 2012-04-01 | 26/07/2012 | 26/07/2012 | NO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-07-01 | 2012-11-15 | DURAMANY SHERIFF | (+232) 33 411 745 | dura_shero@yahoo.com
ADDITIONAL COMENTS: CLOCK: GPS TRANSIT TIMES: LESS THAN 1 MIN COMM LINKS: VSAT stable CHALLENGES: none TRAINING: done
ADDITIONAL COMENTS: CLOCK: GPS TRANSIT TIMES: COMM LINKS: CHALLENGES: TRAINING:
| ANGOLA | YES | COMSOFT AMHS | YES | 2012-04-25 | 2012-04-30 | 2012-06-01 | 2012-06-01 | 2012-06-01 | no | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2012-07-01 | 2012-11-15 | Marcelina Sapalo | +244923501927 | msapalo@enana-ao.com
ADDITIONAL COMENTS: none CLOCK: GPS TRANSIT TIMES: 2 MIN COMM LINKS: reliable CHALLENGES: would like to impliment a domestic VSAT network. TRAINING: completed
| NIGERIA | yes 15/10/2012 | COMSOFT AMHS | New | 2012-10-15 | 2012-10-20 | 2012-11-01 | 2012-11-01 | 2012-11-05 | yes | yes | Thales Eurocat | October 2013 | October 2013 | 2013-10-15 | 2013-10-05 | 2013-10-15 | 2012-11-01 | 2012-11-15 | Nwamkwo Ifeamyi Francis / Olajire Aderemi / Matthew Lawrence Pwajok | (234) 8034710708 / 1 8776675 / (+234)8034531431 / 8024797711 / 8050786333 | ifnwankwo@yahoo.com / aaolajire@yahoo.co.uk / pwajokmathewlawrence@yahoo.com
ADDITIONAL COMENTS: none CLOCK: GPS TRANSIT TIMES: LESS THAN 1 MIN COMM LINKS: AFISNET / VSAT stable CHALLENGES: unreliable power. Deploying UPS and solar systems TRAINING: commenced and on going remaining outstanding to be completed Jun/Jul 2012
FAJS | SOUTH AFRICA | Yes | THALES | yes | 2012-06-01 | 1-6 June 2012 | 2012-06-06 | 7-30 June 2012 | 1 July 2012-14 November 2012 | yes | yes | THALES | same as AIM system | same as AIM system | same as AIM system | same as AIM system | same as AIM system | 2012-09-20 | 2012-11-15 | Lindi-Lee Kirkman / Francois Coetzee | (+27 )119286523 / ©825699852 / 116071281 | Lindik@atns.co.za / Francoisc@atns.co.za
ADDITIONAL COMMENTS: no additional comments. CLOCK: GPS Auto Sync. TRANSIT TIMES: within same min. COMM LINK: On the whole stable. CHALLENGES: with hardware in customs when some VSAT equipment has challenges. Internal system delays - erroneous FPL queue in ATM system or incorrect addressed FPL. response TO MESSAGES - when messages are sent, responses are received. FAJS system auto responds to RQP and RQS messages received.
| ALGERIA | YES | THALES(AERMAC) | PLANNED | N/A | N/A | N/A | N/A | N/A | YES/(EUROCAT+CONVERTER) | to be upgraded | N/A | N/A | N/A | N/A | N/A | N/A | 2012-11-12 | 2012-11-15 | Samail Alili | (+213)21672130/21661504166 | denaccr@enna.dz
NO INFO AVBL. ADDITIONAL COMENTS: CLOCK:GBS TRANSIT TIMES: SAME MIN COMM LINKS: ASYN, X25 AND IP (needs to be upgraded to AMSH) CHALLENGES: TRAINING:
GBYD | GAMBIA | yes | COROBOR | YES | 2012-10-15 | N/A | N/A | 2012-07-26 | 2012-07-26 | no | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-07-26 | 2012-11-15 | Souleymane Jabang | (+220) 4472730/3359922/9962063 | junkung78@hotmail.com
ADDITIONAL COMENTS:CLOCK:GPS TRANSIT TIMES: Within 1 mn COMM LINKS:VSAT/very stable CHALLENGES:Backup VSAT channel & GPS Syn TRAINING:ongoing
ISSUES TO ADDRESS
interface Dakar Recife and Dakar Laspalmas
interface Niamey / Algers and Niamey/Adis
Missing FPL
states that interact with IFPS should participate with the IFPS testing
Nigeria will get back to ATNS on the missing ARIK Air FPL
a key factor could be incorrect AFTN addressing - states should check and verify addresses
check clocks
check transit times
check internal system delays
check links
procedures for message handeling, review and improve or impliment
airlines need to update their address systems
actions
procedures developer: Nigeria, ASECNA, KENYA first draft by end of first week of June and complete work by first week of July. Co-ordinator Nigeria
Air Nav implimentation issues
sesitise the regulator to inform the airlines that they require training too
any other business
include regional officer AIM in documents for circulation
update of FITS
publication date of AIC - ICAO AIMO
apeal to states not to impliment anyother major changes on 15 November 2012