## Sheet1
State | Technical Readiness | Training Status ATS/AIM | Training Airspace Users | Accepting Operational NEW FPL From | RISK | COMMENT | LOP Updated | Action by State
ALGERIA | installed | 70 % completed | on-going | By 12 Nov 12 | VERY LOW RISK |  | No | Update RO by 19 Oct-12
ANGOLA | 2012-10-30 | on-going | on-going | unknown | HIGH RISK | State is not providing updates dispite Regional Office follow-ups | No information | Update RO by 12 Oct -12
BENIN | installed | completed | started | 2012-07-26 | VERY LOW RISK | ASECNA | Yes | Update by 19 Oct-12
BOTSWANA | expected 15-Oct-12 | completed | completed | 2012-11-15 | MEDIUM TO HIGH RISK |  | No | Update RO by 12 Oct -12
BURKINA FASO | installed | completed | started | 2012-07-26 | VERY LOW RISK | ASECNA | ? | Update RO by 19 Oct-12
BURUNDI | installed - awaiting minor software correction | outstanding - awaiting ATNS quote (12 Oct) | not started | 2012-11-15 | MEDIUM RISK | Burundi to request FPL 2012 training from provider | Expected to be signed by end Oct 12 | Update RO by 12 Oct -12
CAMEROON | installed | completed | started | 2012-07-26 | VERY LOW RISK | ASECNA | Yes | Update RO by 19 Oct-12
CAPE VERDE | expected 15-Oct-12. Operational 26-Oct-12 | started | started | from 26 Oct-12 | HIGH RISK |  | Yes | Update RO by 12 Oct -12
CENTRAL AFRICAN REPUBLIC | installed | completed | started | 2012-07-26 | VERY LOW RISK | ASECNA | Yes | Update RO by 19 Oct-12
CHAD | installed | completed | started | 2012-07-26 | VERY LOW RISK | ASECNA | Yes | Update RO by 19 Oct-12
COMOROS | installed | completed | started | 2012-07-26 | VERY LOW RISK | ASECNA | Yes | Update RO by 19 Oct-12
CONGO | installed | completed | started | 2012-07-26 | VERY LOW RISK | ASECNA | Yes | Update RO by 19 Oct-12
COTE D'IVOIRE | AFTN terminal upgrade in progress (ref:PPT) | completed | started | 2012-07-26 | MEDIUM RISK | ASECNA | Yes | Update RO by 12 Oct -12
DEMOCRATIC REPUBLIC OF CONGO | No information provided | No information provided | No information provided | No information provided | HIGH RISK | State is not providing updates dispite Regional Office follow-ups | No information | Update RO by 12 Oct -12
DJIBOUTI | No information provided | No information provided | No information provided | No information provided | HIGH RISK | State is not providing updates dispite Regional Office follow-ups | No information | Update RO by 12 Oct -12
EGYPT | [5 empty] | MID RO to update
EQUATORIAL GUINEA | installed | completed | started | 2012-07-26 | VERY LOW RISK | ASECNA | Yes | Update RO by 19 Oct-12
ERITREA | 2012-10-29 | from 29-Oct-12 | from 29 Oct-12 | 2012-11-11 | HIGH RISK |  | 2012-10-30 | Update RO by 12 Oct -12
ETHIOPIA | installed | completed | completed | 2012-06-30 | VERY LOW RISK |  | 2012-10-15 | Update RO by 19 Oct-12
GABON | installed | completed | started | 2012-07-26 | VERY LOW RISK | ASECNA | Yes | Update RO by 19 Oct-12
GAMBIA | installed | completed | completed | 26-Jul-12 via Dakar | VERY LOW RISK | AIC to be issued | Yes | Update RO by 19 Oct-12
GHANA | installed | on-going | No information provided | 1-Jul-12 ? | MEDIUM RISK | Additional information to be provided | ? | Update RO by 12 Oct -12
GUINEA | installed | completed | not started | Jul-12 Information needs to be updated | LOW RISK | Depending on readiness status in Monrovia | ? | Update RO by 19 Oct-12
GUINEA-BISSAU | installed | completed | started | 2012-07-26 | VERY LOW RISK | ASECNA | Yes | Update RO by 19 Oct-12
KENYA | installed | completed | on-going | 2012-09-20 | VERY LOW RISK |  | Yes | Update RO by 19 Oct-12
LESOTHO | installed - awaiting minor software correction | outstanding - awaiting funding to arrange training | not started | 2012-11-15 | MEDIUM RISK |  | No | Update RO by 12 Oct -12
LIBERIA | installed | completed | not started | Jul-12 Information needs to be updated | LOW RISK |  | ? | Update RO by 19 Oct-12
LIBYA | installed |  |  |  |  | MID RO to update
MADAGASCAR | installed | completed | on-going | 2012-07-26 | VERY LOW RISK | ASECNA | Yes | Update RO by 19 Oct-12
MALAWI | No information provided | No information provided | No information provided | No information provided | HIGH RISK | State is not providing updates dispite Regional Office follow-ups | No information | Update RO by 12 Oct -12
MALI | installed | completed | started | 2012-07-26 | VERY LOW RISK | ASECNA | Yes | Update RO by 19 Oct-12
MAURITANIA | AFTN terminal upgrade in progress (ref:PPT) | completed | started | 2012-07-26 | MEDIUM RISK | ASECNA | Yes | Update RO by 12 Oct -12
MAURITIUS | installed | completed | completed | currently accepting | VERY LOW RISK |  | ? | Update RO by 19 Oct-12
MOROCCO | [5 empty] | EUR/NAT RO to update
MOZAMBIQUE | installed | completed | completed | 2012-10-15 | LOW RISK |  | No | Update RO by 19 Oct-12
NAMIBIA | installed | on-going | from 19-Oct-12 | 2012-10-22 | LOW RISK |  | No | Update RO by 19 Oct-12
NIGER | AFTN terminal upgrade in progress (ref:PPT) | completed | started | 2012-07-26 | MEDIUM RISK | ASECNA | Yes | Update RO by 12 Oct -12
NIGERIA | installation vendor promises before 15 Nov-12 | on-going | from 10-Oct-12 | No information provided | HIGH RISK |  | With Accra | Update RO by 12 Oct -12
REUNION (FRA) |  |  |  |  | LOW RISK
RWANDA | installed - awaiting minor software correction | on-going | completed | week of 11 Oct | MEDIUM RISK | notification for user participation to be issued | No | Update RO by 12 Oct -12
SAO TOME & PRINCIPE | No information provided | No information provided | No information provided | No information provided | HIGH RISK | State is not providing updates dispite Regional Office follow-ups | No information | Update RO by 12 Oct -12
SENEGAL | installed | completed | started | 2012-07-26 | VERY LOW RISK | ASECNA | Yes | Update RO by 19 Oct-12
SEYCHELLES | installed | completed | completed | currently accepting | VERY LOW RISK |  | Expected by 1 Nov-12 | Update RO by 19 Oct-12
SIERRA LEONE | installed | completed | not started | Jul-12. Info needs update | LOW RISK |  | ? | Update RO by 19 Oct-12
SOMALIA | manual-no changes | from 15-Oct to 20 Oct 12 | manual-no changes | from 29-Oct-12 | LOW RISK | agreement to be arranged with adjacebt FIRs. Manual system in place. Notification for user partcipation to be issued by 10 Oct-12 | No | Update RO by 19 Oct-12
SOUTH SUDAN |  | from 11-Oct-12 | 1 week Nov-12 |  |  |  | N/A | Update RO by 19 Oct-12
SOUTH AFRICA | installed | completed | completed | currently accepting NEW FPL | VERY LOW RISK |  | reviewed | Update RO by 19 Oct-12
SUDAN | [5 empty] | MID RO to update | ?
SWAZILAND | installed - awaiting minor software correction | completed | completed | 2012-11-01 | MEDIUM RISK |  | No | Update RO by 12 Oct -12
TOGO | installed | completed | started | 2012-07-26 | VERY LOW RISK | ASECNA | Yes | Update RO by 19 Oct-12
TUNISIA | [5 empty] | EUR/NAT RO to update
UGANDA | 10/22/2012. Currently running AFTN | AIM completed, ATS on-going | 2012-10-18 | 2012-11-10 | MEDIUM RISK | Support agreement with Nairobi signed | Yes | Update RO by 12 Oct -12
UK (BIOT)
UK (ST. HELENA & ASCENSION) | [7 empty] | Update RO by 19 Oct-12
UNITED REPUBLIC OF TANZANIA | 2012-10-22 | AIM training completed, ATS on-going | from 29 Oct -12 | from 7 Nov-12 | HIGH RISK |  | No | Update RO by 12 Oct -12
ZAMBIA | 2013-01-01 | completed | on-going | 2012-10-10 | MEDIUM RISK | Planning interventions to populate legacy systems with PRESENT when received in NEW. Copperchase AFTN to transmit NEW until systems are updated | In progress | Update RO by 12 Oct -12
ZIMBABWE | installed | completed | on-going | 2012-10-10 | LOW RISK | Notam to be issued on 10 Oct 12 | 2012-10-15 | Update RO by 19 Oct-12