## Sheet1
JOHANNESBURG GROUP
Tributary | State | Automated FPL system yes/no | System Vendor | will this be upgraded? | software implementation date | testing date | operational commissioning | ANSP testing date | users testing date | Automated ATM system yes/no | will this be upgraded? | System Vendor | software implementation date | testing date | operational commissioning | ANSP testing date | users testing date | Accepting FPL in new and present format date | Accepting FPL in NEW format only (15 NOV 2012?) | Operational contact person | tel / mobile | e-mail
FAJS | SOUTH AFRICA | Yes | THALES | yes | implemented | completed | operational | ongoing | ongoing | yes | yes | THALES | same as AIM system | same as AIM system | same as AIM system | same as AIM system | same as AIM system | 2012-09-20 | 2012-11-15 | Lindi-Lee Kirkman / Francois Coetzee | (+27 )119286523 / ©825699852 / 116071281 | Lindik@atns.co.za / Francoisc@atns.co.za
Implementation complete.Accepting new fpls.
FBSK | BOTSWANA | yes | Ubitech | yes | delivery expected 13 - 19 Oct 2012 | as soon as equipment is installed 23 Oct | 2012-10-29 | 2012-10-29 | 2012-10-29 | yes | yes | Raytheon | same as AIM system | same as AIM system | same as AIM system | same as AIM system | same as AIM system | 2012-11-15 | 2012-11-15 | Samuel Mbaakanyi / Jobe Malefho | (+267) 368 8200 / (c)72277905 /(c) 71651176 | Smbaakanyi@caab.co.bw / JMalefho@caab.co.bw
Expected delays on ATS system installation. A process has been developed to handle the fpl. Will use free text if deadline is missed.There will be dedicated personnel standing by in case intervention is required.
FCBB | DRC
No in attendance
FDMS | SWAZILAND | no | IAT on VSAT | YES | implemented | completed | partially | completed | mid Oct 12 | no | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2012-11-01 | 2012-11-15 | Francis Kawoya / Nhlanhla Dube | (+268) 25184344 / ©76074828 / 76262182 | fkawoya@gmail.com / nhlanhla@swacaa.co.sz
Outstanding software correction to implement DOF into some ATS messages.
FIMP | MAURITIUS | yes | Copperchase | yes | completed | completed | completed | 2012-06-01 | 2012-07-01 | yes | completed | THALES | completed | completed | completed | same as AIM system | same as AIM system | Currently | 2012-11-15 | Director CAA | (+230) 6032000 | civil-aviation@mail.gov.mu
Operational OJT on going. Awaiting to commence testing with other ANSP and airspace users as they become ready. Missing FPL. Transit times - no problems. Clock linked to ATC system GPS. FPL from Dubai with a 7 min time dif. Manual check also done DLY. issue with UAE flights from Dubai. Trend, for a few days at a time then ok for a while. lesser extent HAJJ flights from Jeddah no FPL. ICAO regional office to provide FIMM with feedback as to who are having challenges with FPL from FIMM.
FLLS | ZAMBIA | yes | Ubitech | yes(new) | 2013-01-04 | 2013-01-28 | 2013-03-18 | 2013-01-28 | 2013-01-28 | no | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2012-10-10 | 2012-11-15 | Stanley Sitali / Jacqueline Malambo | (+260) 211271195 / © 977495215 / © 95282971 | stanley.sitali@lun.aero / jacqueline.malambo@lun.aero
Training of ops staff complete. Airspace user training to be completed 19 Oct 12. manual operations from AFTN until January 2013.
FMMI | MADAGASCAR
Not in attendance
FNLU | ANGOLA
No updates on software delivery and testing
FQMA | MOZAMBIQUE | yes | Copperchase | yes | completed | completed | completed | ongoing | ongoing | no | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2012-10-15 | 2012-11-15 | Joana Agostinho / Dalilo A Amade | (c)(+258) 826516230 /© 828958570 | jomutimba@gmail.com / daliloamade@yahoo.com.br
Contingency plan in place - revert to manual procedures with additional staff.
FSIA | SEYCHELLES | yes | INDRA | yes | completed | completed | completed | ongoing | ongoing | yes | yes | same as AIM system | same as AIM system | same as AIM system | same as AIM system | same as AIM system | same as AIM system | currently | 2012-11-15 | Esmee Samson | 2482527206 | esamson@scaa.sc
New system has variable parameter settings to accommodate a mix of present and new format fpls.
FVHA | ZIMBABWE | yes | Comsoft | yes | completed | completed | completed | ongoing | ongoing | yes | yes | Comsoft | same as AIM system | same as AIM system | same as AIM system | same as AIM system | same as AIM system | 2012-10-07 | 2012-11-15 | Caleb Furawo / Erick Chavunduka | (+263) 4585006 / ©772422031 / © 712867855 | cfurawo@caaz.co.zw / erick@caaz.co.zw
Users will be advised to file new fpls via notam. Training with airspace users is ongoing.
FWLL | MALAWI | YES | Technobrain | yes | 2012-06-15 | 2012-07-01 | 2012-07-30 | 2012-08-01 | 2012-08-01 | yes | yes | Technobrain | same as AIM system | same as AIM system | same as AIM system | same as AIM system | same as AIM system | September/October 2012 | 2012-11-15 | Dixie Kwatani / MFT Bongwe | (+265) 888892494 / ©1770577 / 888867654 / © 1770577 | dkwatani@yahoo.co.uk / donchimtengo@yahoo.com
Will move in line with ATNS VSAT transmission dates. Full commitment from Government in support of this project received in March 2012. - missing FPL - CLOCKS AUTO SYNC WITH GPS. Transit time - no problem. Comm. links - leased lines reliable internal systems delays - NO ALARM TO ALER opr OF MESSAGES in queue, power system unreliable and can cause delays.response to messages - human attitude to responding to messages needs attention.
FXMM | LESOTHO | no | IAT on VSAT | YES | completed | completed | completed | ongoing | 2012-10-25 | no | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2012-11-15 | 2012-11-15 | Ntsontso Joseph Molefi / Jacob Lesekele | (+266) 22350115 / © 58077517 / 22350362 / © 58489404 | jomolefi@graduate.org / jacoblesekele@hotmail.com
Training of ATS staff outstanding - awaiting funding for training provided by ATNS.
FYWH | NAMIBIA | no | Copperchase UK | yes | completed | completed | operational | ongoing | 2012-10-19 | yes | no | THALES / converter (Copperchase) | 2012-10-22 | 22-Oct-12 to 27-Oct-12 | 2012-10-27 | 2012-10-27 | 2012-10-27 | 2012-10-19 | 2012-11-15 | Veronica Kandjabanga-Adeyeye / Hilma Leonard | (+264) 61702080 / © 812470437 / © 812455813 | adeyeyev@dca.com.na / caiso@dca.com.na
Contingency plan - Will revert back to manual if the delivered converter is not operational. Training of ATS staff is still ongoing to reach an expert level.
FZAA | CONGO
Not in attendance
HBBA | BURUNDI | no | IAT on VSAT | YES | completed | completed | partially | ongoing | 2012-10-25 | no | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2012-11-15 | 2012-11-15 | Diomede Ntawuhanakanka | (+257) 78818747 | diontawuhana@yahoo.fr
Have requested training of all staff from ATNS - awaiting feedback. Experiencing a problem with the fpl printer which is currently being investigated.
HRYR | RWANDA | no | IAT on VSAT | yes | completed | completed | partially | ongoing | 2012-10-30 | no | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2012-11-01 | 2012-11-15 | Kamili Kanamugire | (+250) 788857587 | kanamukmli@yahoo.com
ATS staff has been trained and the remainder will be going for training with ATNS 07-Oct-12. ATNS to address a testing quiry.
HTDA | TANZANIA | yes | Egisavia | yes | 2012-05-01 | June/July 2012 | 2012-09-30 | Aug/Sep 2012 | August/September 2012 | yes | yes | Egisavia | same as AIS system | same as AIS system | same as AIS system | same as AIS system | same as AIS system | August/September 2012 | 2012-11-15 | Simon Kessy / Ali Chang'a | (+255) © 754403082 /© 755283680 | skessy@tcaa.go.tz / achanga2004@yahoo.co.uk
Challenge that there is no backup system for AFTN. Missing FPL: clock is GPS sync via network. Transit times are a few seconds time stamp is the same. Comm. links Telecomm company lines are unreliable and take long to repair. This contributes to delays in distribution to ATSU's. Telecomm company network infrastructure is vulnerable thus moving to fibre-optic lines. system generates an error with EOBT and ETD, FPL is rejected, this will be addressed with upgrade. Training/co-operation, Tanzania to inform ICAO regional office WI 7 days
Inter regional hub connections
YBBB | AUSTRALIA
LEEE | SPAIN
SAEZ | ARGENTINA
GOOO | SENEGAL
HKNA | KENYA
FCBB | GABON
Action Items for all states:
Provide training plan to ICAO
Keep ICAO informed re implementation status
Inform ICAO regarding contact person and details and keep them up to date
States to indicate to ICAO regional office that procedures around message handling are in place and are applicable and current and in use. 30 May 2012.
States to communicate by e-mail to the focal points what ATM/CNS systems are in use.
States to advise ICAO regional office and copy participants what IAIP (AIP, AMENDMENT, AIP SUP and AIC) do you have and when was last updated. By 30 May 2012.
VVIP flights - FPL are filed incorrectly (wrong DEP and times etc) FPL laps etc. this needs to be passed to the FPL TF and ask sub group for regional guidance.
As states are ready for testing they are to formally advise the applicable state via e-mail and formal test procedures will be agreed to with specific dates, times and conditions.
ICAO regional office to provide states with an AIC example re fell 2012. www.eurocontrol.int web page provides good guidance material (AIC and Training)
Missing flight plans common problems
Unsynchronised clocks
Delayed transit times
Communication links
Internal system delays
Lack of proper use of service message (RQP/RQS)
No response to query messages
Air Navigation Issues/challenges that impact on FPL -
Zambia - investment in the CNS/ATM infrastructure is challenging despite it being necessary with legacy systems. There is an investment plan in place for the next 5 years.
Swaziland - is currently disposing of legacy equipment that may be useful to other states. Interested states can approach Swaziland and discuss co-operation. It is suggested that on a regional bases we should be aware of who shares similar systems for possible co-operation.
Botswana - communication from ICAO regional office tends to be received late. ICAO informed that states (DG OFFICES) acknowledge receipt of the documents, however they do not seem to filter to the necessary, applicable persons. FPL 2012 focal points are also sent a copy of the invite.
Lesotho - there is a challenge around a requirement for more staff. Challenges around international travel approval and attendance of important meetings.
Malawi - attendance of meetings is not always the correct person( the one who does the job) and they do not train/pass on the information. Task is delegated to someone else who has to work from documentation.
Zimbabwe - lack of knowledge on new terms such as PBN etc… suggesting a new training module to address this challenge. Encourage engineering staff to interact without ICAO facilitation.
Mozambique - the AIS to AIM transmission, there needs to be more localised, sub regional workshops to improve understanding and address challenges
Namibia - applicable ICAO communication doesn’t seem to make it to the applicable people.
Burundi - training for staff is a challenge.
South Africa - the lack of on time aeronautical information