## Heatmap
LIKELIHOOD
IMPACT
1
IMPROBABLE
2
REMOTE
3
OCCASSIONAL
4
PROBABLE
5
FREQUENT
A
CATASTROPHIC
B
SIGNIFICANT
C
MODERATE
D
LOW
E
NEGLIGIBLE
INTOLERABLE
TOLERABLE
ACCEPTABLE
STOP & MITIGATE
MITIGATE
MONITOR
1, 4
1
55
6
5
5
2
55
7
6
7, 8
4
55
2, 4
1
1
10
7
55
1
4
55
2, 3
1, 3
3
RISK
RISK DESCRIPTION
1
Surveillance equipment capabilities SSR/ADS in FRA implementation
2
Air situation Display Systems
3
Processed Surveillance data
4
Use of ATS-DS in FRA
5
Use of VHF/HF/VDL/CPDLC/SATCOM in AIR/GND comm for FRA
6
Use of interoperable systems within AFI
7
Aircraft equipage and State approval/Oversight to enable FRA
8
Regulatory mandate on equipage

## Likelihood Rating
Likelihood Rating Criteria
Likelihood | Description | Value
Frequent | Is expected to occur in most circumstances.The risk event has occurred during the last 3-6 months or is certain to occur in the next 3-6 months | 5
Occasional | Will probably occur at some time. The risk event has occurred during the last 6-12 months or may occur in the next 6-12 months | 4
Remote | Might occur at some time. The risk event has occurred during the last 12-36 months or may occur in the next 12-36 months | 3
Improbable | Could occur at some time. The risk event has occurred during the last 36-60 months or may occur in the next 36-60 months | 2
Extremely improbable | May occur only in exceptional circumstances. | 1

## Impact Rating
Impact Criteria | Impact Rating and Score
| Negligible | Minor | Major | Hazardous | Catastrophic
| E | D | C | B | A
Impact description | No significance to ANS related operational safety. | May egrade or affect normal ANS operational procedures or performance. | Partial loss of significant/ major ANS systems or result in abnormal ANS procedure application. | Complete failure of significant/ major AS systems or result in emergency ANS procedure application. | Serious incidence or accident

## Risk Tolerability Table
Safety Risk Index Range | Safety Risk Description | Recommneded Action (Guidance)
3A, 4A, 4B, 5A, 5B, 5C | INTOLERABLE | STOP OPERATION OR PROCESS IMMEDIATELY. Unacceptable under existing circumstances. Do not permit any operation until sufficient mitigating actions have been implemented to reduce risk index to tolerable or lower if possible. Top Management approval of risk mitigation actions and acceptability required before commencement of affected operation. PMT required to consider and approve the risk mitigation actions
1A, 2A, 2B, 2C, 3B, 3C, 3D, 4C, 4D, 4E, 5D, 5E | TOLERABLE | WARNING. Ensure that risk assessment has been satisfactorily completed and declared preventive controls are in place. Senior management approval of completed risk assessment before commencement of the operation or process. Notification to PMT required
1B, 1C, 1D, 1E, 2D, 2E, 3E | ACCEPTABLE | CAUTION. Perform or review risk mitigation as necessary. Departmental approval of risk assessment required. Notification to PMT optional

## RISK REGISTER
FIR : AFI REGION
FREE ROUTING AIRSPACE
Strategic Objectives Safety, Efficiency, Capacity, Environment
Hazards/Risks & Controls
|  | Operational process, procedure or system | Operational requirement(s)/ Objective | Hazard/Risk Description | Hazard/Risk Reference # | Unsafe event | Key Risk Indicator | Ultimate Consequence | Current defenses | Inherent Risk |  |  | Safety requirements (Actions) | Residual Risk |  |  | Tolerability | Responsible person(s) | Deadline | Remarks
| SUB CATEGORY | [8 empty] | I | L | IRI |  | I | L | RRI |  |  |  |  | 1 | 2 | 3 | 4 | 5
TECHNICAL | TECH: ORGANIZATIONAL FACILITIES | Surveillance | Situational awareness | Surveillance equipment capabilities SSR/ADS in FRA implementation | 1 | 1) Surveillance equipment failure 2) Power Failure | Frequency of occurrence | MAC: Airprox/ ACAS alert/ loss of separation/ (near) midair collisions | 1) Availability of power back up 2) Availability of Multiple surveillance systems | A | 4 | 4A | 1) Procedural control proficiency/Re-currency 2) System redundancies and Contigency plans on FRA 3) Increase of position reporting | A | 2 | 2A | TOLERABLE
|  | Surveillance | Situational awareness | Air situation Display Systems | 2 | Air situation Display failure | Frequency of occurrence | ATM: ATM/CNS) | Installation of primary and secondary control positions | B | 4 | 4B | 1) Procedural control 2) system redudancies | A | 3 | 3A | INTOLERABLE
|  | Surveillance | Situational awareness | Processed Surveillance data | 3 | Unreliable surveillance data | Percentage of incorrect surveillance data | ATM: ATM/CNS) | scheduled data integrity monitoring | A | 4 | 4A | Service level agreements with system providers | A | 3 | 3A | INTOLERABLE
|  | Communication | Enhanced interfacility coordination | Use of ATS-DS in FRA | 4 | Communication Failure ATS-DS | Frequency of occurrence | MAC: Airprox/ ACAS alert/ loss of separation/ (near) midair collisions | HF Service | A | 4 | 4A | VSAT for tielines | A | 2 | 2A | TOLERABLE
TECHNICAL | TECH: ORGANIZATIONAL FACILITIES | Communication | Enhanced Air/ground Com Failure | Use of VHF/HF/VDL/CPDLC/SATCOM in AIR/GND comm for FRA | 5 | Failure of Air ground communication suing either VHF/HF/VDL/CPDLC | Frequency of occurrence | MAC: Airprox/ ACAS alert/ loss of separation/ (near) midair collisions | 1) Use of multiple ground communications channels 2) Secondary frequencies | B | 4 | 4B | 1) Installation of additional power back-up 2) Deploy additonal comm channels 3) Utilize ATS-DS for interfacility coordination 4) Contigency routes/plans | B | 4 | 4B | INTOLERABLE
|  | Communication | Enhanced system supported coordination | Use of interoperable systems within AFI | 6 | Inadequate interoperability (AIDC/OLDI/AMHS/Surveillance) | Percentage rate of service unavailability | MAC: Airprox/ ACAS alert/ loss of separation/ (near) midair collisions | 1) Use of multiple connection channels | C | 3 | 3C | Upgrade of internet connectivity | C | 3 | 3C | TOLERABLE
|  | Aircraft Capability |  | Aircraft equipage and State approval/Oversight to enable FRA | 7 | Inadequate Avionics capability/approval/Continous Oversight | 1) Percentage of fleet that are not adequately equiped 2) Percentage of Aircraft not approved | MAC: Airprox/ ACAS alert/ loss of separation/ (near) midair collisions | 1) Adequate guidance material 2) Inreased surveillance | C | 3 | 3C | Improve inspector capacity | C | 2 | 2C | TOLERABLE
|  | Aircraft Capability |  | Regulatory mandate on equipage | 8 | Inadequate regulatory framework to mandate Equipage | Percentage of regulatory provisions not reviewed | MAC: Airprox/ ACAS alert/ loss of separation/ (near) midair collisions | 1) Guidance on rule making | C | 2 | 2C | Enhance stakeholder engagement | C | 2 | 2C | TOLERABLE
|  | Navigation | Airspace capacity | GNSS Signal availability, accuracy and integrity
|  | Navigation | Airspace capacity | Unavailability of VOR/DME
|  | Navigation | Airspace capacity | Inappropriate Navigation Specifications
|  | Navigation | Airspace capacity | Lack of harmonized Instrument flight procedures/specifications/standards
|  | Ground-based safety nets/Conflict Detection tools | Enhanced Situational Awareness | Failure of safety nets/conflict detection tools
ORGANIZATIONAL | ORG: OPERATIONAL POLICIES/PROCEDURES | Flight Planning | Coordination | Missing flight plans
|  | Availability of Aeronautical information |  | Inefficient/outdated Publications AIP/
|  | ANS provision | Capacity & Efficiency | Unavailability/degraded of Air Navigation Service
ORGANIZATIONAL | ORG: OPERATIONAL POLICIES/PROCEDURES | FUA | Airspace efficiency | Inadequate civil miltary coordination
|  | ATFM | Airspace efficiency | Inadequate ATFM
|  | Provision of Weather information | Airspace efficiency | Unavailability of Met Information (Reliable/updated)
|  | LoAs/SoPs/SSIs/Contigency plans | Enhanced FIR coordination | Inadeqaute LoAs/SoPs/SSIs/CPs
HUMAN | HUM: PHYSICAL LIMITATION | Personnel Capacity |  | ATS staff capacity(competence/Number)
|  | Change management |  | Inadequate Management of Change to FRA
ATCO Workload
HUMAN | HUM: PSYCHOLOGICAL |  |  | Personnel Motivation
Complacency
Human Machine interaction
Ergonomics
Interdepartmental collaboration
Just Culture
ORGANIZATIONAL | ORG: OPERATIONAL POLICIES/PROCEDURES | Airspace Complexity (To be considered at State level) |  | Inefficient existing route network/Airspace concept
Mixed Traffic Operations
Identification of Entry/Exit/Intermediate points
Note on C6: Author: Describe the main process/procedure/system being subjected to this assessment e.g FIR Coordination, Communication, e.t.c
Note on D6: Author: Describe the oerational objective e.g Enhanced cross FIR coordination
Note on E6: Author: Describe the assigned or targetted Hazard
Note on G6: Author: Describe the projected Unsafe Event. If more than one Unsafe Event, address them under separate raw
Note on I6: Author: Describe the projected Ultimate Consequence.