## MET2 2023 Action Plan
Plan d'action - MET2- Année 2023
Deliverables | Référence & Titre de l'élément ASBU | Enablers | Ref. of activity | Tasks | Beneficiary States | Expected outcomes/Achievements | Responsible | Supporting Body/Person | Status | Date and references of evidences of completion | Comments
Deliverable 1.1
Coordination of the Project and implementation guidance material | AMET B1 |  | 1.1.0 | Provide quartrly report on the implementation of project activities | 2023 target States | Reports | PTC | Project Team Members | Ongoing | Quartely Report
| AMET B1 |  | 1.1.1 | Confirm MET Project Team membership | All States | Project team composition | PTC | ICAO | In Progress | 05/05/2023 | PTC to follow up with Regional Officers
| AMET B1 |  | 1.1.2 | Update meeting on the Project methodology and expected outcomes | MET2 Members | Minutes of the meeting | PTC | ICAO | Not started | 10/05/2023
| AMET B1 |  | 1.1.3 | Develop project costing | All AFI States | Project costing developed | PTC | ICAO | Not started | 2023-06-30
Deliverable 1.2
Status of implementation ASBU elements, Gaps analysis and development of implementation Action Plan | AMET B1 |  | 1.2.0a | Establish regulatory framework for the implementation of AMET-B1 | All target States | National regulation integrated the framework for the implmentation of AMET-B1 elements | Target States CAA | PTC and tasked experts | Not started | 2023-06-30
| AMET B1 |  | 1,2,0b | Update MET2 members on the the AMET-B1 elements applicable to the region | MET2 Members | MET2 members updated on the AMET-B1 elements | PTC | ICAO | Not started | 2023-05-30
| AMET B1 |  | 1,2,1,a) | Review and perform gaps analysis of States on ASBU implementation data | Bostwana, Somalie, Rwanda, South Africa, Burkina Faso | ASBU status analysis report | Olebile | PTC | In Progress | 2023-05-30 | Verify compliance on the level of implementation of the ASBU elements of the 15 target states (Botswana, Somalia, South Africa, Rwanda, Burkina, Cameroon, Comoros, Congo, Gabon, Chad, Niger, Togo, Madagascar, Nigeria, and Senegal) that will be assisted during 2023
| AMET B1 |  | 1,2,1,b) | Review and perform gaps analysis of States on ASBU implementation data | Cameroun, Comoros, Congo Brazza, Gabon, Niger | ASBU status analysis report | Issoufou Abdoulaye | PTC | In Progress | 2023-05-30
| AMET B1 |  | 1,2,1,c) | Review and perform gaps analysis of States on ASBU implementation data | Senegal, Chad, Togo, Madagascar, Nigeria | ASBU status analysis report | Alpha M M DIALLO | PTC | In Progress | 2023-05-30
| AMET B1 |  | 1,2,1,d) | Assist States in developing ASBU nation action plan in MET | Bostwana, Somalia, Rwanda, South Africa, Burkina Faso | ASBU status analysis report | Olebile | PTC | In Progress | 2023-06-15
| AMET B2 |  | 1,2,1,e) | Assist States in developing ASBU nation action plan in MET | Cameroun, Comoros, Congo Brazza, Gabon, Niger | ASBU status analysis report | Issoufou Abdoulaye | PTC | In Progress | 2023-06-15
| AMET B3 |  | 1,2,1,f) | Assist States in developing ASBU nation action plan in MET field | Senegal, Chad, Togo, Madagascar, Nigeria | ASBU status analysis report | Alpha M M DIALLO | PTC | In Progress | 2023-06-15
| AMET B1 |  | 1,2,1,g) | Assist States to identify / review/update/development of project implementation guidance material | Bostwana, Somalie, Rwanda, South Africa, Burkina Faso | List of Identified documents References of updated developped documents | Olebile | PTC | Not started | 2023-06-30
| AMET B1 |  | 1,2,1,h) | Assist States to identify / review/update/development of project implementation guidance material | Cameroun, Comoros, Congo Brazza, Gabon, Niger | List of Identified documents References of updated developped documents | Issoufou Abdoulaye | PTC | Not started | 2023-06-30
| AMET B1 |  | 1,2,1,i) | Assist States to identify / review/update/development of project implementation guidance material | Senegal, Chad, Togo, Madagascar, Nigeria | List of Identified documents References of updated developped documents | Alpha M M DIALLO | PTC | Not started | 2023-06-30
| AMET B1 |  | 1.2.1.k) | Review and update of the AMBEX handbook | All states | AMBEX handbook updated | Iro Mahmane | PTC MET 2 PTC COM4 ICAO | Not started | 2023-12-31
Deliverable 1.3
Monitoring and assistance State in the Implementation of State Action Plan
| AMET B1 |  | 1.3.1 | Update States on the AMET-B1 elements and the use of Excel tool to collect ASBU implementation data | All target States | States familiarised with the use of Excel tool | PTC | ICAO | Not started | 2023-06-30
| AMET B1 |  | 1.3.2 | Review/Check the relevance of ASBU data provided by states and provide guidance for correction if any | All target States | Report analysis | PTC | Target states | Not started | 2023-05-15
| AMET B1 |  | 1.3.3 | Provide assistance to States MET operational procedures | Chad, Somalia, Comoros, Burkina Faso, Togo | MET operational procedures developed | PTC | Project Experts | Not started | 31/05/ 2023
| AMET B1 |  | 1.3.4 | Workshop on the developement of Capabilities to exchange Meteorological information in ICAO Meteorological Information Exchange Model (IWXXM) | All target States | Target States provided with knowledge and understanding of capabilities to be developed to implement the IWXXM | PTC | Project Experts | Not started | 30/06/2023
|  |  | 1.3.5 | Coordinate the assistance activities conducted by PTEs | Target states | timely completion of assigned tasks | PTC | ICAO | in progess | 2023-12-31
|  |  | 1.3.6 | Provide monthly report to the PTC on the implementation of the activities of assistance to States | Target states | Monthly reports | PTE | PTC | Not started | Monthly | Starting from June
|  |  | 1.3.7 | Provide quarterly and annual Report on the progress of the Project activities | Target states | Reports | PTC | PTE | In progress | Quarterly

## Target States
ASBU ELEMENTS
STATES | AMET B1/1 | AMET B1/2 | AMET B1/3 | AMET B1/4
TME en %
Bostwana | 72 | 28 | 100 | 66
Somalie | 0 | 0 | 0 | 66
Rwanda | 76 | 30 | 100 | 33
Afrique du Sud | 88 | 100 | 100 | 100
Burkina Faso | 0 | 0 | 0 | 66
Cameroun | 54 | 33 | 0 | 66
Comores | 75 | 55 | 0 | 100
Congo | 58 | 85 | 0 | 66
DRC
Gabon | 4 | 0 | 0 | 66
Niger | 94 | 83 | 0 | 66
Sénégal | 100 | 88 | 0 | 66
Tchad | 100 | 33 | 0 | 66
Togo | 0 | 0 | 0 | 66
Madagascar | 82 | 100 | 0 | 66
Nigeria | 52 | 16 | 100 | 33
TME= Taux de mise en œuvre
Les elements non applicable ne sont pas pris en compte dans le decompte du N pour la formule
(n/N*100)

## Feuil1
Bostwana
Somalie
Rwanda
Afrique du Sud
Burkina Faso
Cameroun (Douala)
Comores
Congo Brazza (Brazza)
Gabon (libreville)
Niger (Niamey)
Sénégal (Dakar Djass)
Tchad (Ndjamena)
Togo (Lome)
Madagascar
Nigeria