## Sheet1
EXAMPLE PROJECT PLAN
|  | ACTIVITY | Timeline Number of WorkDays | Parallel Days | Total Work Days | Start Date | Completion Date
PLAN | 1 | Agree on Operational Requirements | 10 | 0 | 10 | 2013-02-09 | 2013-02-22
| 2 | Create Airspace Design Team | 5 | 0 | 5 | 2013-02-22 | 2013-03-01
| 3 | Agree on Objectives, Scope & Timeline | 20 | 0 | 20 | 2013-03-01 | 2013-03-29
| 4 | Analyze Reference Scenario | 15 | 0 | 15 | 2013-03-29 | 2013-04-19
| 5 | Select Safety Criteria, Safety Policy, & Performance Criteria | 10 | 0 | 10 | 2013-04-19 | 2013-05-03
| 6 | Agree on CBS/ATM Assumptions | 12 | 0 | 12 | 2013-05-03 | 2013-05-21
DESIGN | 7 | Design Airspace Routes and Holds | 14 | 0 | 14 | 2013-05-21 | 2013-06-10
| 8 | Initial Procedure Design | 20 | 0 | 20 | 2013-06-10 | 2013-07-08
| 9 | Design Airspace Volumes and Sectors | 20 | 0 | 20 | 2013-07-08 | 2013-08-05
| 10 | Confirm ICAO Navigation Specification | 5 | 0 | 5 | 2013-08-05 | 2013-08-12
VALIDATE | 11 | Airspace Concept Validation | 20 | 0 | 20 | 2013-08-12 | 2013-09-09
| 12 | Finalize Procedure Design | 22 | 0 | 22 | 2013-09-09 | 2013-10-09
| 13 | Procedure Validation | 20 | 0 | 20 | 2013-10-09 | 2013-11-06
IMPLEMENT | 14 | ATC System Integration | 20 | 10 | 30 | 2013-10-23 | 2013-12-04
| 15 | Awareness and Training Material | 0 | 30 | 30 | 2013-10-23 | 2013-12-04
| 16 | Implementation | 1 | 0 | 1 | 2013-12-04 | 2013-12-05
| 17 | Post Implementation Review | 30 | 0 | 30 | 2013-12-05 | 2014-01-16
|  |  | 244 |  | 284 | total | END DATE
|  | TIMELINE DAYS REQUIRED |  |  |  | workdays | 2014-01-16
*note: Uses xl WORKDAY function to exclude weekend and holiday days
| DIRECTIONS: | Type in START DATE in cell G3, then fill in cells D3 thru D19 and cells E3 thru E19 as appropriate.
Worksheet will then calculate start and end dates for each subsequent activity.
Formulas:
Completion Date = WORKDAY([Start Date],[Timeline Number of WorkDays])
Completion Date = WORKDAY([Completion Date, row above],[Timeline Number of WorkDays])
Start Date = WORKDAY([Completion Date],-[Total Work Days])