## New Format
MEVA II PROGRAM NEW CIRCUITS REQUEST and OPEN ISUES TRACKING
MEVA II NEW CIRCUITS REQUEST | [17 empty] | Updated: 9 May 2014
Requestor Site | Type of Circuit | TO | Date Requested | Submitted Quote | Received "OK" Process | Submitted Serv. Order | Received Signed SO | Received Init. Payment | Placed Equip. Order | Received Equipment | Shipped to Site | Installed & Tested | Loaded Config. Files | Executed Config. Files | System Checked | Circuit Activation | Start of Service | Remarks
Havana, Cuba
| 1 ea. CPM/LAM 9.6 Kbps (pending) | Miami, FL | 2012-02-27 | 2012-09-10 | 2012-09-21 | 2012-10-18 | 2013-03-22 | [10 empty] | On Hold
| 1 ea. AMHS 64 Kbps | Atlanta, GA | 2012-02-27 | 2012-09-10 | 2012-09-21 | 2012-10-18 | 2013-03-22 | 2013-04-29 | 5/3/2013 PO-0000796 | 2013-07-08 | 2013-10-02 | 2013-10-03 | 2013-10-03 | 2013-10-03 | 2013-10-04 | 2013-10-04 | 2013-11-01 | New Memotec was installed configured and ready for the new circuit testing & implementation. COMPLETED
| 1 ea. RADAR 9.6 Kbps | Kingston, Jamaica | 2012-02-27 | 2012-09-10 | 2012-09-21 | 2012-10-18 | 2013-03-22 | 2013-04-29 | 5/3/2013 PO-0000796 | 2013-07-08 | 2013-10-02 | 2013-10-03 | 2013-10-03 | 2013-10-03 | 2013-10-04 | 2013-10-04 | 2013-11-01 | New Memotec was installed configured and ready for the new circuit testing & implementation. COMPLETED
| 1 ea. RADAR 9.6 Kbps | COCESNA, Honduras | 2012-02-27 | 2012-09-10 | 2012-09-21 | 2012-10-18 | 2013-03-22 | 2013-04-29 | 5/3/2013 PO-0000796 | 2013-07-08 | 2013-10-02 | 2013-10-03 | 2013-10-03 | 2013-10-03 | 2013-10-04 | 2013-10-04 | 2013-11-01 | New Memotec was installed configured and ready for the new circuit testing & implementation. COMPLETED
| 1 ea. RADAR 9.6 Kbps (pending) | Merida, Mexico | 2012-02-27 | 2012-09-10 | 2012-09-21 | 2012-10-18 | 2013-03-22 | [10 empty] | On Hold
| 1 ea. Voice Shut Down | Merida, Mexico | 2012-02-27 | 2012-09-10 | 2012-09-21 | 2012-10-18 | 2013-03-22 | 2013-04-29 | 5/3/2013 PO-0000796 | 2013-07-08 | 2013-10-02 | 2013-10-03 | 2013-10-03 | 2013-10-03 | 2013-10-04 | 2013-10-04 | 2013-11-01 | New Memotec was installed configured and ready for the new circuit testing & implementation. COMPLETED
| 1 ea. Voice Shout Down | Merida, Mexico
| 1 ea. Voice Shout Down | Miami, FL
Curacao
| 1 ea. Voice Shout Down | Caracas, Venezuela | 2012-10-01 | 2012-10-10 | 2012-10-23 | SO -0004 26-Oct-2012 | 2012-12-13 | 2023-04-15 | 25 Apr 2013 PO-0000794 | 2013-07-09 | 2013-07-23 | 2013-07-24 | 2013-10-08 | 2013-10-17 | 2013-10-17 | 2017-10-17 | 2013-11-01 | 17 Oct 13 - Loaded and executed the new configurations files. Notified Luis and asked to check the circuit 18 Oct 13 - Luis informed that Curacao switch need to be configured and he will work with Caracas 28 Jan 2014 - Have not received notification from Luis that Curacao switch has been re-configured. The switch at Curacao need to be re-configured, Luis will work with Curacao
| 1 ea. Voice Shout Down | Oranjestad, Aruba | 2012-10-01 | 2012-10-10 | 2012-10-23 | SO -0004 26-Oct-2012 | 2012-12-13 | 2023-04-15 | 25 Apr 2013 PO-0000794 | 2013-07-09 | 2013-07-23 | 2013-07-24 | 2013-07-24 | 2013-07-25 | 2013-07-25 | 2013-08-30 | 2013-09-01 | Successful test was performed between both site. 20 Jan 14 - Jean requested suspension of this circuit with Aruba because the line has not been in use. CLOSED
| 1 ea. Voice Shout Down | Kingston, Jamaica | 2012-10-01 | 2012-10-10 | 2012-10-23 | SO -0004 26-Oct-2012 | 2012-12-13 | 2023-04-15 | 25 Apr 2013 PO-0000794 | 2013-07-09 | 2013-07-23 | 2013-07-24 | 2013-07-24 | 2013-11-14 | 2013-11-14 | 2013-11-14 | 2013-12-01 | Deposit received, circuit activated, and test tone test successfully completed. CLOSED
| 1 ea. Voice Shout Down (PENDING) | Santo Domingo | 2012-10-01 | 2012-10-10 | 2012-10-23 | SO -0004 26-Oct-2012 | 2012-12-13 | 2023-04-15 | 2013-04-25 | 2013-07-09: 2013-07-09; 2013-07-23: 2013-07-23; 2013-07-24: 2013-07-24; 2013-07-24: 2013-07-24 | Santo Domingo has not approved this circuit
| 1 ea. AMHS 1/2 Circuit | Atlanta | 2012-10-01 | 2012-10-22 | 2012-10-23 | SO -0004 26-Oct-2012 | 2012-12-13 | 2023-04-15 | 25 Apr 2013 PO-0000794 | 2013-07-09: 2013-07-09; 2013-07-23: 2013-07-23; 2013-07-24: 2013-07-24; 2013-07-24: 2013-07-24 | Waiting on Atlanta to schedule activation
San Juan, PR
| 1 ea. Voice Shout Down | Sint Maarten | 2012-02-04 | 2012-03-15 | 2012-02-04 | N/A | N/A | 2012-03-01 | 2012-10-29 | 2012-11-06 | 2012-11-30 | 2012-11-30 | 2013-02-13 | 2013-02-14 | 2013-02-14 | 2013-07-16 | 2013-08-01 | Successful test was performed between both site. CLOSED
| 1 ea. Voice Shout Down | Santo Domingo | 2012-02-04 | 2012-03-15 | 2013-03-04 | N/A | N/A | 2012-03-01 | 2013-03-14 | 2013-03-22 | 2013-05-29 | 2013-05-29 | 2013-06-26 | 2013-06-26 | 2013-06-26 | 2013-07-16 | 2013-08-01 | Successful test was performed between both site. CLOSED
| 4 ea. Switched Voice | Sint Maarten | 2013-01-29 | [6 empty] | 2013-11-14: 2013-11-14; 2013-12-01: 2013-11-14
| 1 ea. Radar 9.6kbps (new) | Sint Maarten | 2013-01-29 | 2013-02-21 | [13 empty] | 24 Jan 2014 - Have not received the "Go-Ahead" to install the new hardware in San Juan. 31 Mar 2014 - Still waiting for a "go" from Dulce for the hardware purchase installation in San Juan
| 1 ea. Voice Shout Down | Sint Maarten
COCESNA
| 1 ea. RADAR 9.6 Kbps | Cuba |  | 2012-09-10 | 2012-10-01 | SO-0002 22-Oct-2012 R 5-Nov-2012 | 2012-12-18 | 2013-06-27 | N/A | N/A | N/A | N/A | 2014-01-07 | 2014-01-07 | 2014-02-06 | 7 Fe 2014 | 2014-05-01 | 28 Jan 14 - Both Memotec are configured and changes made as per Moises request regarding changing port at the COCESNA site. Changes have been made and confirmed that both system are connected. Waiting for status from COCESNA 7 Feb 2014 - COCESNA informed that the radar circuit test with Cuba was completed and they were able to pass data. COMPLTED
| 1 ea. Voice Shout Down (Test Circuit) | Jamaica |  | 2012-11-27 | 2012-11-28 | SO-0003 28-Nov-2012 |  | Jamaica is paying | N/A | N/A | N/A | N/A | 2012-12-12 | 2012-12-12 | 2012-12-13 |  |  | 28 Jan 14 - A new DAV circuit card and a E&M SLIM have been shipped and received at COCESNA. Waiting for notification from Moises indicating that the new DAV & E&M SLIM have been installed. 25 Mar 2014 - AIS installed the new DAV card and resumed tone tseting. After many hours of testing, they were not able to pass the tone. Troubleshooting continued
Merida
| 1 ea. Switched Voice | Various sites | 2010-02-01 | 2012-02-17 | 2012-05-17 | SO-0001 31-Aug-12 | 2012-09-25 | 2012-09-27 | 2012-03-20 |  |  |  | 2012-10-17 | 2012-10-17 | 21-Nov-2013 28-Feb-2013 | 2013-02-28 | 2013-03-01 | Circuit intermittent issues corrected and tested. CLOSED
| 1 ea. Switched Voice | Various sites | 2010-02-01 | 2012-05-15 | 2012-05-17 | SO-0001 31-Aug-12 | 2012-09-25 | 2012-09-27 | 2012-03-20 |  |  |  | 2012-10-17 | 2012-10-17 | 21-Nov-2013 28-Feb-2013 | 2013-02-28 | 2013-03-01 | Circuit intermittent issues corrected and tested. CLOSED
| 1 ea. Voice Shout Down | Cuba | 2010-02-01 | 2012-05-15 | 2012-05-17 | SO-0001 31-Aug-12 | 2012-09-25 | 2012-09-27 | 2012-03-20 | [8 empty] | 29 Jan 14 - Merida Site is "OFF" and can not load the configuration files. Working with ICAO Mexico to send a new MSA to Sergio to re -activate this site. MSA is in progress
| 1 ea. AFTN (pending) | Cuba | 2010-02-01 | 2012-05-15 | 2012-05-17 | SO-0001 31-Aug-12 | 2012-09-25 | 2012-09-27 | 2012-03-20 | [8 empty] | 29 Jan 14 - Merida Site is "OFF" and can not load the configuration files. Working with ICAO Mexico to send a new MSA to Sergio to re -activate this site. MSA is in progress
| 1 ea. AFTN (pending) | Cuba
Aruba
| 1 ea. Voice Shout Down | Curacao |  | 2012-10-10 | 2012-11-20 | SO-0002 - 25 Oct 2012 SO's;003, 004 & 005 - 6 Feb 2013 | SO - 0002 - 5-Dec-12 | SO-0002 26-Feb-2013 | 2013-03-22 | 2013-03-29 | 2012-04-23 | 2012-04-24 | 2013-05-02 | 2013-05-03 | 2013-05-04 | 2013-08-30 | 2013-09-01 | Successful test was performed between both site. 22 Jan 14 - Joselito requested a cancellation of this circuit due to mayor equipment investment to complete the 4-wire connection. CLOSED
Caracas
| 1 ea. Voice Shout Down | Curacao | 2012-10-01 | 10-Oct-2012 3-Sep-2013 | 2013-09-03 | N/A | N/A |  | N/A | N/A | N/A | N/A | 2013-10-17 | 2013-10-17 | 2013-10-17 | 2013-10-17 |  | 7 Oct 13 - Received Caracas configuration files and forwarded to Luis 17 Oct 13 - Luis informed that configuration files have been loaded and activated. 18 Oct 13 - Luis informed that Curacao switch need to be configured and he will work with Caracas 29 Jan 14 - Waiting confirmation that Curacao switch has been configured. The switch at Curacao need to be re-configured, Luis will work with Curacao
Dominican Republic
| 1 ea. Voice Shout Down | San Juan | 2013-02-28 | 2013-03-04 | 2013-04-29 | SO-0004 29 Apr 2013 | 2013-06-23 | 2013-05-22 | 2013-05-22 | 2013-06-24 | 2013-06-26 | 2013-06-26 | 2013-06-26 | 2013-06-26 | 2013-06-26 | 2013-07-16 | 2013-08-01 | Successful test was performed between both site. COMPLETED
| 1 ea. Voice Shout Down (PENDING) | Curacao | 2012-09-28 | 2012-10-10 | 2012-10-22 | SO-0003 23 -Oct-2012 | [11 empty] | 18 Jun 2013 - Fernando informed that both sites have not reached an agreement on this circuit and will probably be done at the end of 2013.
| 1 ea. AMHS 1/2 Circuit | FAA Atlanta | 2004-09-04 | 2012-09-26 | 2012-10-02 | SO-0002 2-Oct-2013 R 18 Oct 12 | 2012-11-13 | 2012-11-16 | 2012-11-20 | 2012-11-19 | 2012-11-20 | 2012-12-20 | 2012-12-20 | 2012-12-20 | 2012-12-21 | 2013-04-03 | 2013-05-01 | Used a card from spares and re-order a replacement. AMHS circuit is COMPLETE
Miami
| 1 ea. CPN/LAN 9.6 Kbps (Pending) | Cuba | 2012-09-01 | [14 empty] | On Hold
Jamaica
| 1 ea. Voice Shout Down | Curacao |  | 2012-10-10 | 2012-10-19 | SO-0005 19-Oct=2012 | 2012-10-22 | 2013-08-29 | 2012-11-27 | 2012-11-29 | 2012-12-03 | 2012-12-12 | 2012-12-12 | 2013-10-30 | 2013-10-30 | 2013-11-14 | 2013-12-01 | Configuration files loaded and activated. Test tone successfully completed. CLOSED
| 1 ea. Radar 9.6Kbps | Cuba |  | 2012-10-10 | 2012-10-19 | SO-0005 19-Oct=2012 | 2012-10-22 | 2013-08-29 | 2012-11-27 | 2012-11-29 | 2012-12-03 | 2012-12-12 | 2012-12-12 | 2013-10-30 | 2013-10-30 | 2013-10-04 | 2013-12-01 | Configuration files loaded and activated. CLOSED
| 1 ea. Voice Shout Down (Test Circuit) | COCESNA |  | 2012-11-27 | 2012-11-28 | SO-0006 28-Nov-2012 |  |  | N/A | N/A | N/A | 2012-12-12 | 2012-12-14 | 2012-12-14 | 2012-12-17 | 2013-12-17 |  | 28 Jan 14 - AIS technician discovered a bad DAV or E&M SLIM in COCESNA. A new DAV with new E&M SLIM was shipped & received in COCESNA. Testing will Resume as soon COCESNA install the new hardware. 25 Mar 2014 - AIS installed the new DAV card in COCESNA and resumed tone tseting. After many hours of testing, they were not able to pass the tone. Troubleshooting continued
| 1 ea. AMHS 1/2 Circuit | Atlanta |  | 2012-10-10 | 2012-10-18 | SO-0004 17-Oct-2012 | 2012-10-18 | 2012-11-27 | 2012-11-29 | 2012-12-03 | 2012-12-12 | 2012-12-12 | 2012-12-14 | 2012-12-14 | 2012-12-17 |  |  | 31 Jan 14 - Waiting on Atlanta to schedule activation & testing
FAA Atlanta | 1 ea. AMHS 1/2 Circuit (Port 2) | Dominican Republic | 2011-01-01 | 2011-01-06 | 2013-01-07 | N/A | N/A |  | 2012-10-01 | 2012-10-12 | 2012-11-01 | 2012-11-15 | 2012-12-12 | 2012-12-14 | 2012-12-17 | 2013-04-03 | 2013-05-01 | COMPLETED
| 1 ea. AMHS 1/2 Circuit (Port 5) | Havana, Cuba |  | 2011-01-06 | 2013-01-07 | N/A | N/A |  | 2012-10-01 | 2012-10-12 | 2012-11-01 | 2012-11-15 | 2014-03-25 | 2014-03-26 | 2014-03-26 | 2014-03-26 |  | 25 Feb 14 - Received a request from FAA to start circuit activation. Started checking system configuration. ETC: 7 Mar 14 25 Mar 2014 - New configuration files were loaded and activated. Wainting on Cuba to start testing
| 1 ea. AMHS 1/2 Circuit (Port 3) | Curacao |  | 2011-01-06 | 2013-01-07 | N/A | N/A |  | 2012-10-01: 2012-10-01; 2012-10-12: 2012-10-12; 2012-11-01: 2012-11-01; 2012-11-15: 2012-11-15 |  | 31 Jan 14 - Waiting on Atlanta to schedule activation & testing
| 1 ea. AMHS 1/2 Circuit (Port 1) | Jamaica | 2011-01-01 | 2011-01-06 | 2013-01-07 | N/A | N/A |  | 2012-10-01: 2012-10-01; 2012-10-12: 2012-10-12; 2012-11-01: 2012-11-01; 2012-11-15: 2012-11-15 |  | 31 Jan 14 - Waiting on Atlanta to schedule activation & testing
| 1 ea. AMHS 1/2 Circuit (Port 4) | Saint Marten |  | 2011-01-06 | 2013-01-07 | N/A | N/A |  | 2012-10-01: 2012-10-01; 2012-10-12: 2012-10-12; 2012-11-01: 2012-11-01; 2012-11-15: 2012-11-15 |  | 25 Feb 14 - Received a request from FAA to start circuit activation. Started checking system configuration. ETC: 7 Mar 14. Will also need a contract modification to add additional circuitrs
St. Maarten
| 1 ea. AMHS 1/2 Circuit | FAA Atlanta | 2013-03-05 | 2013-03-07 | 2013-03-07 | SO-0003 22-Feb-2013 R 12-Mar-2013 | 2013-05-20 | 2013-06-06 | 6/19/2013 PO-0000824 | 2013-07-08 | 2013-07-12 | 2013-10-09 | 2013-10-09 | 2013-10-09 | 2013-10-09 | 2013-11-14 | 2013-11-14 | New V.24 card installed 13 Nov 2013. COMPLETED
| 4 ea. Switched Voice (new) | San Juan | 2013-01-29 | 2013-01-31 | 2013-02-18 | SO-0003 22-Feb-2013 R 12-Mar-2013 | 2013-05-20 | 2013-06-06 | 6/19/2013 PO-0000824 | 2013-07-08 | 2013-07-12 | 2013-10-09 | 2013-10-09 | 2013-10-09 | 2013-10-09 | 2013-10-30 | 2013-11-01 | Installation COMPLETED
| 1 ea. Radar 9.6kbps (new) | San Juan | 2013-01-29 | 2013-01-31 | 2013-02-18 | SO-0003 22-Feb-2013 R 12-Mar-2013 | 2013-05-20 | 2013-06-06 | 6/19/2013 PO-0000824 | 2013-07-08 | 2013-07-12 | 2013-10-09 | 2013-10-09 | 2013-10-09 | 2013-10-09 | 2013-11-14 | 2013-11-14 | New V.24 card installed 13 Nov 2013. COMPLETED
| 1 ea. Voice Shout Down | San Juan | 2012-02-01 | 2012-02-06 | 2012-02-08 | SO-0002 14-Feb2012 | 2012-02-17 | 2012-05-31 |  |  |  |  | 2013-01-16 | 2013-01-16 | 2013-01-17 | 2013-06-01 | 2013-06-01 | Successful test was performed between both site. COMPLETED
| I ea. Switched Voice | San Juan | 2012-02-01 | 2012-02-06 | 2012-02-08 | SO-0002 14-Feb2012 | 2012-02-17 | 2012-05-31 |  |  |  |  | 2013-05-02 | 2013-05-03 | 2013-05-06 | 2013-05-06 | 2013-05-06 | COMPLETED
OTHER ONGOING ACTIVITIES
Date Open | Originator | Date Closed | Description |  |  | Remarks
17 Sep 2013 - Replaced the antenna
2012-10-02 | Curacao (Cedric) | CLOSED | 3.8M Antenna replacement
2013-01-18 | Panama (Abdiel H. Vasquez) | CNACELLED - CLOSED | Installation of a new MEVA system in the new building |  |  | 17 Apr 13 - SES contracts department sent the official quote to ICAO Montreal. Notified Abdiel to work with ICAO Montreal to accelerate the approval 23 May 13 - Abdiel informed that they are making payment arrangements 13 Jun 13 - Panama requested an updated quote 14 Jun 2013 - Sent the updated quote, waiting response. 22 Aug 13 - Sent a status request to ICAO Montreal. 28 Mar 2014 - ICAO Montreal cancelled this job | bar: 2013-07-08
2013-05-07 | Gran Cayman (Keith) |  | Elevation Jack Screw Replacement |  |  | 15 May 13 - Keith informed that the antenna EL jack screw need replacement. 9 May 13 - Submitted a price quote for the jack screw replacement
2013-05-09 | Santo Domingo (Keith) | CLOSED | Elevation Jack Screw Replacement |  |  | 9 May 2013 - Submitted price quote 15 May 2013 - Santo Domingo informed that they are not replacing the screw at this time. They are buying a new antenna latter on
2013-06-17 | Cuba (Keith) | CLOSED | C-Band feed |  |  | 3 Oct 2013 - Replaced the C-Band feed
2013-06-18 | COCESNA & Merida (Keith) | CLOSED | C-Band Band Pass Filter |  |  | 21 Jun 2013 - Place filters on order. PO# 0000825 11 Jul 2013 - Received the band pass filters. 12 Jul 2013 - Shipped to site 19 Jul 2013 - Delivered to the site
2013-06-05 | Haiti (Emmanuel) | CLOSED | Request feed support replacement |  |  | 18 Nov 2013 - Parts were received but NOT installed. The SES field engineer discovered that they only needed cleaning. Parts were cleaned and painted during the annual maintenance.
2013-07-16 | Sint Maarten | CLOSED | Ring Voltage Booster & CAT5E |  |  | 19 Aug 2013 - Raul confirmed receive of the Ring Booster and CAT 5E shielded cable
2013-07-16 | Santo Domingo (Dom Rep) | CLOSED | 4-Wire telephone |  |  | 18 Nov 2013 - Shipped the phones to the site
2013-09-03 | Yves Andre Cesar Haiti) | CLOSED | 4-Wire telephone |  |  | Delivered the phones on 17 Jan 2014