## New Format
MEVA II NEW CIRCUITS PENDING ACTIVATION as per TMG28 MEETING
Updated: 3 Dec 2014
Requestor Site | Type of Circuit | TO | Date Requested | Submitted Quote | Received "OK" Process | Submitted Serv. Order | Received Signed SO | Received Init. Payment | Placed Equip. Order | Received Equipment | Shipped to Site | Installed & Tested | Loaded Config. Files | Executed Config. Files | System Checked | Circuit Activation | Start of Service | Remarks
| 1 ea. Voice Shout Down | Merida, Mexico
| 1 ea. Voice Shout Down | Miami, FL
Curacao | 1 ea. AMHS 1/2 Circuit | Atlanta | 2012-10-01 | 2012-10-22 | 2012-10-23 | SO -0004 26-Oct-2012 | 2012-12-13 | 2023-04-15 | 25 Apr 2013 PO-0000794 | 2013-07-09 | 2013-07-23 | 2013-07-24 | 2013-07-24 |  |  |  |  | Not in contract
San Juan, PR | 4 ea Switch voice circuits | Sint Maarten | 2014-06-18 | 2014-07-10 | [13 empty] | ICAO working with Sint Maarten for payment responsibility. Submitted price proposal. Received notification from Lloyd Hinds indicating that these circuits are ON-HOLD
| 1 ea. Radar 9.6kbps (new) | Sint Maarten | 2013-01-29 | 2014-07-10 | [13 empty] | ICAO working with Sint Maarten for payment responsibility. Submitted price proposal. Received notification from Lloyd Hinds indicating that these circuits are ON-HOLD
| 1 ea. Voice Shout Down | Sint Maarten
Jamaica | 1 ea. AMHS 1/2 Circuit | Atlanta |  | 2012-10-10 | 2012-10-18 | SO-0004 17-Oct-2012 | 2012-10-18 | 2012-11-27 | 2012-11-29 | 2012-12-03 | 2012-12-12 | 2012-12-12 | 2012-12-14 | 2012-12-14 | 2012-12-17 |  |  | Not in contract
FAA Atlanta | 1 ea. AMHS 1/2 Circuit (Port 3) | Curacao |  | 2011-01-06 | 2013-01-07 | N/A | N/A |  | 2012-10-01 | 2012-10-12 | 2012-11-01 | 2012-11-15 | [5 empty] | Not in Contract
| 1 ea. AMHS 1/2 Circuit (Port 1) | Jamaica | 2011-01-01 | 2011-01-06 | 2013-01-07 | N/A | N/A |  | 2012-10-01 | 2012-10-12 | 2012-11-01 | 2012-11-15 | [5 empty] | Not in Contract
| 1 ea. AMHS 1/2 Circuit (Port 4) | Saint Marten |  | 2011-01-06 | 2013-01-07 | N/A | N/A |  | 2012-10-01 | 2012-10-12 | 2012-11-01 | 2012-11-15 | [5 empty] | Not in Contract
St. Maarten | 4 ea Switch Voice Circuits | San Juan | 2013-01-29 | 2013-01-31 | 2013-02-18 | SO-0003 22-Feb-2013 R 12-Mar-2013 | 2013-05-20 | 2013-06-06 | 6/19/2013 PO-0000824 | 2013-07-08 | 2013-07-12 | 2013-10-09 | 2013-10-09 | 2013-10-09 | 2013-10-09 | 2013-10-30 | 2013-11-01 | Hardware already installed, waiting on San Juan hardware installation & configuration. ON HOLD
| 1 ea. AMHS 1/2 Circuit | FAA Atlanta | 2013-03-05 | 2013-03-07 | 2013-03-07 | SO-0003 22-Feb-2013 R 12-Mar-2013 | 2013-05-20 | 2013-06-06 | 6/19/2013 PO-0000824 | 2013-07-08 | 2013-07-12 | 2013-10-09 | 2013-10-09 | 2013-10-09 | 2013-10-09 | 2013-11-14 | 2013-11-14 | Hardware already installed, configured and ready for activation, waiting on FAA to add to the contract
| 1 ea. Radar 9.6kbps (new) | San Juan | 2013-01-29 | 2013-01-31 | 2013-02-18 | SO-0003 22-Feb-2013 R 12-Mar-2013 | 2013-05-20 | 2013-06-06 | 6/19/2013 PO-0000824 | 2013-07-08 | 2013-07-12 | 2013-10-09 | 2013-10-09 | 2013-10-09 | 2013-10-09 | 2013-11-14 | 2013-11-14 | Hardware already installed, waiting on San Juan hardware installation & configuration. ON-HOLD
Indicate that hardware is already installed, configured and ACTIVE
Not configured or activated
ON-HOLD