## CAR Intl ADs
AERODROME CERTIFICATION IMPLEMENTATION PLAN - CAR REGION (Janaury 2022)
STATE/TERRITORY | No of AERODROMES (Doc. 8733, Vol. II, FASID, Table AOP 1) | RESPONSIBLE BODY | NUMBER OF AERODROMES
|  |  | Certified | On-going | Starting date | End date | Planned | Remarks
Central America | 16 |  | 6 | 4 |  |  |  |  | 4.0541 | %
Belize | 1 | BCAA | 0 | 1 | Jan-2015 |  |  | 29 August 2019 3 phase
Costa Rica | 4 | DGAC | 1 | 1 | Jan-2015
El Salvador | 2 | AAC | 1
Guatemala | 3 | DGAC | 1 |  |  | 2017-10-01
Honduras | 5 | AHAC | 2 | 2 |  |  |  | San Pedro Sula Certified 040419, Roatan in 171219
Nicaragua | 1 | INAC | 1 |  |  | 2016-09-01
Central Caribbean | 98 |  | 67 | 13 |  |  |  |  | 45.2703 | %
Aruba | 1 | DCA | 1 | 0
Bahamas | 2 | BCAA | 1 | 1 | jan-2016 | June-2016 |  | BCAA reuqested the removal of 8 aerodromes due to lack of infraestructure, services & equipment
Bermuda | 1 | ASSI/UK | 1
Bonaire | 1 | Netherlands Civil Aviation Authority | 1 | 0
Cayman Islands (UK) | 2 | ASSI/UK | 2 | 0
Cuba | 10 | IACC | 5 | 4
Curacao | 1 | CCAA | 1 | 0
Dominican Republic | 8 | IDAC | 7 | 3 | jan-2016 |  | June 2018 | Puerto Plata Feb 2018; Barahona June 2018; La Romana June 2018,
Haiti | 2 | OFNAC | 0 | 0
Jamaica | 3 | JCAA | 2 | 1 |  |  |  | NMIA Certified October 19
Mexico | 64 | AFAC | 43 | 4 | 2009 | 2021 | 20
Turks and Caicos Islands (UK) | 3 | ASSI/UK | 3
Eastern Caribbean | 34 |  | 20 | 2 |  |  |  |  | 13.5135 | %
Anguilla (UK) | 1 | ASSI/UK | 1
Antigua and Barbuda | 1 | ECCAA | 0
Barbados | 1 | BCAD | 1
Dominica | 2 | ECCAA | 0
French Antilles | 4 | DRAC | 4
Grenada | 2 | ECCAA/CAD | 0
Montserrat (UK) | 1 | ASSI/UK | 1
Saba | 1 | Netherlands Civil Aviation Authority | 1
Sint Eustatius | 1 | Netherlands Civil Aviation Authority | 1
Puerto Rico (USA) | 4 | FAA | 4
Saint Kitts and Nevis | 2 | ECCAA | 0
Saint Lucia | 2 | ECCAA | 0 | 1
Saint Vincent and the Grenadines | 5 | ECCAA | 0 | 1
Sint Maarten | 1 | Department of Civil Aviation & Shipping and Maritime DCASM | 1
Trinidad and Tobago | 2 | TTCAA | 2
Virgin Islands (UK) | 2 | ASSI/UK | 2
Virgin Islands (USA) | 2 | FAA | 2
TOTAL | 148 |  | 93 | 19 |  | 0 |  |  | 62.8378 | %
|  |  | 62.8378 | %

## AD Certified & RST
CAR Regional Aerodrome Certification Implementation Plan - CRACIP
State/Territory |  | Aerodromes | Certified | Planned Aerodrome Certification * |  |  |  |  | Aerodrome Traffic density** |  |  | Runway Safety Team |  | CAPSCA Programme |  | A-CDM
| ICAO CODE |  |  | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Light | Medium | Heavy | RST implemented | RST to be implemented | Assistance Visit AV | Action Plans | <25% implemented | 25% - 40% implemented
Central America |  |  | 6 | [8 empty] | 3 | 5 | 5 | 1 | 7 |  | RST CA | 4.1096 | %
Belize | MZBZ | BELIZE/Philip S.W. Goldson Intl |  | X | X | X |  |  | X |  |  | 1 |  | 1
Costa Rica | MROC | ALAJUELA/Juan Santamaría Intl. | 1 | X | X | X | X | X |  | X |  |  | 1 | 1 |  | 1
| MRLB | LIBERIA/Daniel Oduber Quirós |  | X | X |  |  |  | X |  |  |  | 1 |  |  | 1
| MRLM | LIMÓN/Limón Intl |  | X |  |  |  |  | X
| MRPV | PAVAS/Tobías Bolaños Intl. |  | X |  |  |  |  | X
El Salvador | MSLP | SAN SALVADOR/ Apto Intl Mons. Oscar Arnulfo Romero y Galdames | 1 | X | X | X | X | X | X |  |  |  | 1 | 1 | 1 | 1
| MSSS | SAN SALVADOR/ Ilopango Intl |  | X | X |  |  |  | X
Guatemala | MGGT | GUATEMALA/La Aurora | 1 | X | X | X | X | X | X |  |  |  | 1 | 1 |  | 1
| MGMM | SANTA HELENA/Mundo Maya Intl. |  | X | X
| MGPB | PUERTO BARRIOS/ Puerto Barrios
Honduras | MHLM | SAN PEDRO SULA/Ramón Villeda Morales | 1 | X | X | X | X | 2019-04-04 |  | X |  | 1 |  |  |  | 1
| MHLC | LA CEIBA/Goloson Intl |  | X
| MHTG | TEGUCIGALPA/Toncontín Intl |  | X
| MHRO | ROATÁN/Juan Manuel Gálvez Intl. | 1 | X | X |  |  | 2019-12-17 | X | [6 empty] | 1
| MHPR | COMAYAGUA/Aeropuerto Intl. Palmerola |  | X | X
Nicaragua | MNMG | MANAGUA/Augusto César Sandino Intl | 1 | X | X | X | X | X | X |  |  | 1 | 1 | 1 |  | 1
Central Caribbean |  |  | 67 | [8 empty] | 65 | 14 | 9 | 5 | 14 |  | RST CC | 89.0411 | %
Aruba | TNCA | ORANJESTAD/Reina Beatrix International Airport | 1 | X | X | X | X | X | X |  |  | 1 |  | 1
Bahamas | MYGF | FREEPORT/ Grand Bahama International Airport |  | X |  |  |  |  | X |  |  |  | 1
| MYNN | NASSAU/Lynden Pindling International Airport | 1 | X | X | X | X | X | X |  |  |  | 1 | 1 |  | 1
Bermuda (UK) | TXFK | BERMUDA/L.F. Wade | 1 | X | X | X | X | X | [7 empty] | 1
Bonaire | TNCB | KRALENDIJK/Flamingo, Bonaire I. | 1 | X | X | X | X | X |  |  |  |  | 1
Cayman Islands (UK) | MWCB | CAYMAN BRAC/Charles Kirkconnell Intl. | 1 | X | X | X | X | X | [7 empty] | 1
| MWCR | GEORGETOWN/Owen Roberts Intl | 1 | X | X | X | X | X
Cuba | MUCM | CAMAGUEY/Ignacio Agramonte | 1 | X | X | X | X | X |  |  |  | 1
| MUCL | CAYO LARGO DEL SUR/Vilo Acuña |  | X | [8 empty] | 1
| MUCC | CAYO COCO/Jardines del Rey | 1 | X | X | X | X | X |  |  |  | 1
| MUCF | CIENFUEGOS/Jaime González |  | X | X | X | [6 empty] | 1
| MUHA | HABANA/José Martí | 1 | X | X | X | X | X |  |  |  | 1 |  | 1 | 1 | 1
| MUHG | HOLGUÍN/Frank País |  | X | X | X | [6 empty] | 1
| MUMZ | MANZANILLO/Sierra Maestra |  | X | X | [7 empty] | 1
| MUSC | SANTA CLARA/Abel Santamaría |  | X | X | X | [6 empty] | 1
| MUCU | SANTIAGO DE CUBA/ Antonio Maceo | 1 | X | X | X | X | X |  |  |  | 1
| MUVR | VARADERO/Juan Gualberto Gómez | 1 | X | X | X | X | X |  |  |  | 1 |  |  |  | 1
Curacao | TNCC | WILLEMSTAD/Hato, Curaçao I. | 1 | X | X | X | X | X |  |  |  |  | 1
Dominican Republic | MDBH | BARAHONA/Apto. Internacional María Montes |  | X | X | X | [6 empty] | 1
| MDLR | LA ROMANA/Casa de Campo Intl. | 1 | X | X | X | X | X |  |  |  |  | 1
| MDPP | PUERTO PLATA/ Gregorio Luperón Intl. | 1 | X | X | X | X | X |  |  |  | 1
| MDPC | PUNTA CANA/Punta Cana Intl. | 1 | X | X | X | X | X |  |  |  |  | 1 |  |  | 1
| MDST | SANTIAGO/Cibao Intl. | 1 | X | X | X | X | X |  |  |  |  | 1
| MDSD | SANTO DOMINGO/Jose Francisco Peña Gomez Intl. | 1 | X | X | X | X | X |  |  |  | 1 |  | 1 | 1 | 1
| MDCY | SAMANA/El Catey Intl. | 1 | X | X | X | X | X |  |  |  | 1
| MDJB | HIGUERO/Dr. Joaquín Balaguer Intl. | 1 | X | X | X | X | X |  |  |  | 1
Haiti | MTCH | CAP HAITIEN/Cap Haitien Intl
| MTPP | PORT-AU-PRINCE/Port-au-¬Prince Intl | [10 empty] | 1 | 1
Jamaica | MKJP | KINGSTON/Norman Manley Intl | 1 | X | X | X | X | X |  |  |  | 1 |  | 1 |  | 1
| MKJS | MONTEGO BAY/Sangster Intl | 1 | x | x | x | x | x |  |  |  | 1 |  |  |  | 1
| MKBS | OCHO RIOS/Ian Fleming Intl.
México | MMAA | ACAPULCO/Gral. Juan N. Alvarez Intl. RS | [6 empty] | X |  |  | 1
| MMAS | AGUASCALIENTES/Aeropuerto Jesús Terán | 1 | X | X | X | X | 2016 | X |  |  | 1
| MMBT | BAHÍAS DE HUATULCO/Bahías de Huatulco | 1 | X | X | X | X | 2016 | X |  |  | 1
| MMSL | CABO SAN LUCAS/Cabo San Lucas | [6 empty] | X
| MMCP | CAMPECHE/Ing. Alberto Acuña Ongay | 1 | X | X | X | X | 2012 | X |  |  | 1
| MMUN | CANCÚN/Cancún Intl. | 1 | X | X | X |  | 2019 |  |  | X | 1 |  | 1 | 1 | 1
| MMCM | CHETUMAL/Chetumal Intl. | 1 | X | X | X | X | 2018 | X |  |  | 1
| MMCT | CHICHEN-ITZA/Chichen Itza | [6 empty] | X
| MMCU | CHIHUAHUA/General de División y Piloto Aviador Roberto Fierro Villalobos | 1 | X | X | X | X | 2019-10-01 | X |  |  | 1
| MMMC | CIUDAD ACUÑA/Cuidad Acuña Intl. | [6 empty] | X
| MMCE | CIUDAD DEL CARMEN/Ciudad del Carmen Intl | 1 | X | X | X | X | 2012 | X |  |  | 1
| MMCN | CIUDAD OBREGON/Ciudad Obregon | 1 | X | X | X | X | 2012 | X |  |  | 1
| MMCV | CIUDAD VICTORIA/General Pedro José Méndez | 1 | X | X | X | X | 2013 | X |  |  | 1
| MMCS | CIUDAD JUÁREZ/Abraham González Intl. | 1 | X | X | X | X | 2017 | X |  |  | 1
| MMCZ | COZUMEL/Cozumel Intl. | 1 | X | X | X | X | 2016 | X |  |  | 1 |  | 1 | 1
| MMCB | CUERNAVACA/General Mariano Matamoros | [6 empty] | X |  |  | 1
| MMCL | CULIACÁN/Culiacán | 1 | X | x | x | x | 2019-10-01 | X |  |  | 1
| MMDO | DURANGO/Durango | [6 empty] | X |  |  | 1
| MMGL | GUADALAJARA/Miguel Hidalgo Costilla Intl. | 1 | X | X | X | X | 2019-05-01 |  |  | X | 1 |  |  |  | 1
| MMGM | GUAYMAS/Gral. José María Yáñez Intl. | 1 | X | X | X | X | 2011 |  | X |  | 1
| MMHO | HERMOSILLO/Aeropuerto Internacional General Ignacio Pesqueira García | 1 | X | X | X | X | 2015 |  | X |  | 1
| MMZH | IXTAPA-ZIHUATANEJO/ Ixtapa-Zihuatanejo Intl. | 1 | X | X | X | X | 2016 | X |  |  | 1
| MMLP | LA PAZ/Gral. Manuel Márquez de León Intl. | 1 | X | X | X | X | 2015 | X |  |  | 1
| MMLO | LEÓN/Aeropuerto Internacional de Guanajuato | 1 | X | X | X | X | 2016 | X |  |  | 1
| MMLT | LORETO/Loreto Intl | 1 | X | X | X | X | 2012 | X |  |  | 1
| MMLM | LOS MOCHIS/Del Valle del Fuerte | 1 | X | X | X | X | 2017 |  | X |  | 1
| MMZO | MANZANILLO/Playa de Oro Intl. | 1 | X | X | X | X | 2016 | X |  |  | 1
| MMMA | MATAMOROS/Matamoros Intl | 1 | X | X | X | X | 2013 | X |  |  | 1
| MMMZ | MAZATLAN/Gral. Rafael Buelna Intl. | 1 | X | X | X | X | 2017 | X |  |  | 1
| MMMD | MERIDA/Lic. Manuel Crescencio Rejón Intl. | 1 | X | X | X | X | 2017 | X |  |  | 1
| MMML | MEXICALI/Gral. Rodolfo Sánchez Taboada Intl. | 1 | X | X | X | X | 2016 |  | X |  | 1
| MMMX | MÉXICO/Aeropuerto Internacional Benito Juárez, Ciudad de México |  | X | [6 empty] | X | 1 |  | 1 | 1 | 1
| MMMT | MINATITLAN/Minatitlan | [6 empty] | X |  |  | 1
| MMMV | MONCLOVA/Venustiano Carranza | [6 empty] | X
| MMAN | MONTERREY/Del Norte Intl. | [6 empty] | X
| MMMY | MONTERREY/Gral. Mariano Escobedo Intl. | 1 | X | X | X | X | 2014 |  | X |  | 1 |  |  |  | 1
| MMMM | MORELIA/Gral. Francisco J. Mujica Intl. | 1 | X | X | X | X | 2016 |  | X |  | 1
| MMNG | NOGALES/Nogales Intl. | [6 empty] | X |  |  | 1
| MMNL | NUEVO LAREDO/ Aeropuerto Internacional Quetzalcóatl | 1 | X | X | X | X | 2012 | X |  |  | 1
| MMOX | OAXACA/Xoxocotlan | 1 | X | X | X | X | 2016 | X |  |  | 1
| MMPQ | PALENQUE/Palenque RS
| MMPG | PIEDRAS NEGRAS/ Piedras Negras Intl. | [6 empty] | X
| MMPB | PUEBLA/Hermanos Serdan | 1 | X | X | X | X | 2017 | X |  |  | 1
| MMPS | PUERTO ESCONDIDO/Puerto Escondido | [6 empty] | X |  |  | 1
| MMPE | PUERTO PEÑASCO/Aeropuerto del Mar de Cortes | [6 empty] | X
| MMPR | PUERTO VALLARTA/ Lic. Gustavo Diaz Ordaz Intl. | 1 | X | X | X | X | 2014 | X |  | X | 1 |  |  |  | 1
| MMQT | QUERETARO/Intercontinental de Querétaro | 1 | X | X | X | X | 2009 | X |  |  | 1
| MMRX | REYNOSA/Gral. Lucio Blanco Intl. | 1 | X | X | X | X | 2018 |  |  |  | 1
| MMIO | SALTILLO/Plan de Guadalupe | [6 empty] | X
| MMSF | SAN FELIPE/San Felipe Intl. | [8 empty] | X
| MMSD | SAN JOSÉ DEL CABO/ Aeropuerto Internacional Los Cabos | 1 | X | X | X | X | 2014 | X |  |  | 1
| MMSP | SAN LUIS POTOSI/Ponciano Arriaga | 1 | X | X | X | X | 2017 | X |  |  | 1
| MMSM | SANTA LUCIA/Aeropuerto Intl. Felipe Angeles |  | X | X
| MMTM | TAMPICO/Gral. Francisco Javier Mina Intl. |  | X |  |  |  |  | X |  |  | 1
| MMTP | TAPACHULA/Tapachula Intl | [6 empty] | X |  |  | 1
| MMEP | TEPIC/Tepic Intl | 1 | X | X | X | X | 2017 |  |  | X | 1
| MMTJ | TIJUANA/Gral. Abelardo L. Rodríguez Intl. | 1 | X | X | X | X | 2014 | X |  | X | 1
| MMTO | TOLUCA/Jose María Morelos y Pavón | 1 | X | X | X | X | 2011 | X |  |  | 1
| MMTC | TORREÓN/Francisco Sarabia | 1 | X | X | X | X | 2016 | X |  |  | 1
| MMTG | TUXTLA GUTIERREZ/Angel Albino Corzo | 1 | X | X | X | X | 2019-05-01 | X |  |  | 1
| MMPN | URUAPAN/General Ignacio López Rayón | 1 | X | X | X | X | 2014 | X |  |  | 1
| MMVR | VERACRUZ/Gral. Heriberto Jara Intl. | 1 | X | X | X | X | 2017 | X |  |  | 1
| MMVA | VILLAHERMOSA/Capitán P.A. Carlos Rovirosa | 1 | X | X | X | X | 2016 | X |  |  | 1 | [5 empty] | Total RST MX | 53
| MMZC | ZACATECAS/Aeropuerto General Leobardo C. Ruiz Intl. | [9 empty] | 1 | [5 empty] | Total AC MX | 43 | 64 Ads
Turks and Caicos Islands (UK) | MBGT | GRAND TURK/Grand Turk Intl | 1 | X | X | X | X | X
| MBPV | PROVIDENCIALES/ Providenciales Intl | 1 | X | X | X | X | X
| MBSC | SOUTH CAICOS/South Caicos Intl | 1 | X | X | X | X | X
Eastern Caribbean |  |  | 20 | [8 empty] | 5 | 6 | 2 | 0 | 4 |  | RST EC | 6.8493 | %
Anguilla (UK) | TQPF | THE VALLEY/ Clayton J. Lloyd Intl. Airport | 1 | X | X | X | X | X | X | [6 empty] | 1
Antigua and Barbuda | TAPA | SAINT JOHNS/ V.C. Bird International Airport | [6 empty] | X |  |  | 1 |  |  |  | 1
Barbados | TBPB | BRIDGETOWN/Grantley Adams Intl | 1 | X | X | X | X | X | X |  |  | 1 |  | 1
Dominica | TDPD | MARIGOT/Melville Hall International Airport | [6 empty] | X
| TDCF | ROSEAU/Canefield Intl. | [6 empty] | X
French Antilles | TFFF | FORT-DE-FRANCE/Le Lamentin, Martinique | 1 | X | X | X | X | X |  | X
| TFFR | POINTE-À-PITRE/Le Raizet, Guadeloupe | 1 | X | X | X | X | X |  | X
| TFFJ | SAINT BARTHELEMY/ Saint Barthelemy, Guadeloupe | 1 | X | X | X | X | X |  |  | X
| TFFG | SAINT MARTIN/Grand Case, Guadeloupe | 1 | X | X | X | X | X | X
Grenada | TGPZ | LAURISTON / Carriacou I. | [6 empty] | X
| TGPY | SAINT GEORGES /Maurice Bishop Intl. |  | X |  |  |  |  | X |  |  |  | 1
Montserrat (UK) | TRPG | GERALD´S / John A. Osborne | 1 | X | X | X | X | X | X | [6 empty] | 1
Saba | TNCS | THE BOTTOM/Juancho E. Yrausquin, Saba | 1 | X | X | X | X | X | X |  |  |  | 1
Sint Eustacius | TNCE | ORANJESTAD/F.D. Roosevelt, Saint Eustatius I. | 1 | X | X | X | X | X | X |  |  |  | 1
Puerto Rico | TJBQ | AGUADILLA/Rafael Hernández Intl | 1 | X | X | X | X | X | X
| TJPS | PONCE/Ponce-Mercedita | 1 | X | X | X | X | X | X
| TJSJ | SAN JUAN/Luis Muñoz Marín Intl | 1 | X | X | X | X | X |  | X
| TJVQ | VIEQUES/Antonio Rivera | 1 | X | X | X | X | X | X
Saint Kitts and Nevis | TKPK | BASSETERRE/Robert L. Bradshaw, Saint Kitts I. | [6 empty] | X |  |  |  | 1
| TKPN | CHARLESTOWN/Newcastle Nevis I. | [6 empty] | X
Saint Lucia | TLPC | CASTRIES/George F. L. Charles | [6 empty] | X
| TLPL | VIEUX-FORT/Hewanorra Intl |  | X | X |  |  |  | X |  |  |  | 1
Saint Vincent and the Grenadines | TVSB | BEQUIA/J.F. Mitchell | [6 empty] | X
| TVSC | CANOUAN/Canouan | [6 empty] | X
| TVSA | KINGSTOWN/Argyle Intl | [6 empty] | X |  |  |  | 1
| TVSM | MUSTIQUE/Mustique | [6 empty] | X
| TVSU | UNION ISLAND/Union Island | [6 empty] | X
Sint Maarten | TNCM | PHILIPSBURG/Princess Juliana, Sint Maarten | 1 | X | X | X | X | X |  |  | x | 1
Trinidad and Tobago | TTPP | PORT OF SPAIN/Piarco Intl, Trinidad I. | 1 | X | X | X | X | X | X |  |  | 1 |  | 1 |  | 1
| TTCP | SCARBOROUGH/Crown Point, Tobago I. | 1 | X | X | X | X | X | X |  |  | 1
Virgin Islands (UK) | TUPJ | ROADTOWN/Beef Island | 1 | X | X | X | X | X | X
| TUPW | VIRGIN GORDA I./Virgin Gorda | 1 | X | X | X | X | X | X
Virgin Islands (USA) | TISX | CHRISTIANSTED/Henry E. Rohlsen, St. Croix | 1 | X | X | X | X | X | X
| TIST | SAINT THOMAS/Cyril E. King | 1 | X | X | X | X | X | X
|  | TOTAL | 93 | [7 empty] | Total: | 73 | 25 | 16 | 6
* Aerodrome certifcation process:
Phase 1: Dealing with the expression of interest by an intending applicant for the aerodrome certifcate;
Phase 2: Assessing the formal application, including evaluation of the aerodrome manual;
Phase 3: Assesing the aerodrome facilities and equipment;
Phase 4: Issuing or refusing an aerodrome certifcate;
Phase 5: Promulgating the certified status of an aerodrome and the required details in the AIP
** Aerodrome Traffic Density
a) Light. The number of movements in the mean busy hour is not greater than 15 per runway or typically less than 20 total aerodrome movements.
b) Medium. The number of movements in the mean busy hour is of the order of 16 to 25 per runway or typically between 20 to 35 total aerodrome movements.
c) Heavy. The number of movements in the mean busy hour is of the order of 26 or more per runway or typically more than 35 total aerodrome movements.
Note 1. The number of movements in the mean busy hour is the arithmetic mean over the year of the number of
movements in the daily busiest hour.
Note 2. Either a take-off or a landing constitutes a movement.
*** RST Implementation based on:
1.- Aerodrome traffic density.
2.- Visibility conditions: 1) Visibility sufficient for the pilot to taxi and to avoid collision with other traffic on taxiways and at intersections by visual reference, and for personnel of control units to exercise control over all traffic on the basis of visual surveillance; 2) Visibility sufficient for the pilot to taxi and to avoid collision with other traffic on taxiways and at intersections by visual reference, but insufficient for personnel of control units to exercise control over all traffic on the basis of visual surveillance; and 3) Visibility less than 400 m RVR (low visibility operations).