## Sheet1
[9 empty] | FPLT TF/5 WP/3 | [12 empty] | FPLT TF/5 WP/3
[9 empty] | Appendix B | [12 empty] | Appendix B
JOHANNESBURG FCWM SUMMARY SHEET (Birchwood Hotel, 8-9 May 2012)
Tributary | country | Automated FPL system yes/no | System Vendor | will this be upgraded? | software implementation date | testing date | operational commissioning | ANSP testing date | users testing date | Automated ATM system yes/no | will this be upgraded? | System Vendor | software implementation date | testing date | operational commissioning | ANSP testing date | users testing date | Accepting FPL in new and present format date | Accepting FPL in NEW format only (15 NOV 2012?) | Operational contact person | tel / mobile | e-mail
FAJS | South Africa | Yes | THALES | yes | 2012-06-01 | 1-6 June 2012 | 2012-06-06 | 7-30 June 2012 | 1 July 2012-14 November 2012 | yes | yes | THALES | same as AIM system | same as AIM system | same as AIM system | same as AIM system | same as AIM system | 2012-09-20 | 2012-11-15 | Lindi-Lee Kirkman / Francois Coetzee | (+27 )119286523 / ©825699852 / 116071281 | Lindik@atns.co.za / Francoisc@atns.co.za
No additional comments. MISSING FPL - Clocks - GPS Auto Sync. Transit times - within same min. Comm. links. On the whole stable. Challenges with hardware in customs when some VSAT equipment has challenges. Internal system delays - erroneous FPL queue in ATM system or incorrect addressed FPL. response TO MESSAGES - when messages are sent, responses are received. FAJS system auto responds to RQP and RQS messages received.
FBSK | Botswana | yes | Ubitech | yes | 1-30 sep 2012 | 1-30 Sep 2012 | 2012-09-30 | 2012-10-01 | 2012-10-01 | yes | yes | Raytheon | same as AIM system | same as AIM system | same as AIM system | same as AIM system | same as AIM system | 2012-10-01 | 2012-11-15 | Samuel Mbaakanyi / Jobe Malefho | (+267) 368 8200 / (c)72277905 /(c) 71651176 | Smbaakanyi@caab.co.bw / JMalefho@caab.co.bw
Proposal expected from Raytheon / Ubitech on 14 May 2012 and expect to sign soon there after. Will send ICAO regional office update by 19 May 2012. MISSING FPL - task force formed. Clocks on GPS auto sync. Message switch clock is sometimes behind, timer stops running then manual intervention to restart. transit times delays, requires review. comm. links - local links on telecom, can be unreliable and take time to be restored. Internal system delays - messages queue at FDPS and must be manually manipulated or deleted. FMS stops running occasionally, system shows TX but still in queue for TX. FPL for following day only shows on position an hour before deep, so times out before the DEEP time. Botswana to provide ICAO regional office with report and plan to address the problems regarding missing FPL (9 June 2012).
FCBB | DRC
No in attendance
FDMS | Swaziland | no | VSAT - ATNS | YES | 2012-06-01 | 2012-06-01 | 2012-06-01 | 2012-06-01 | 2012-07-01 | no | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2012-10-01 | 2012-11-15 | Francis Kawoya / Nhlanhla Dube | (+268) 25184344 / ©76074828 / 76262182 | fkawoya@gmail.com / nhlanhla@swacaa.co.sz
No further comments. Missing FPL. Clocks synchronised manually with FAJS area control sector via telephone. Transit times - no noticeable difference. Comm. links - VSAT AVBL good. internal system delays occasionally due to manual faxing of FPL to ATC and distance that has to be walked.
FIMP | Mauritius | yes | Copperchase | yes | completed | completed | completed | 2012-06-01 | 2012-07-01 | yes | completed | THALES | completed | completed | completed | same as AIM system | same as AIM system | Currently | 2012-11-15 | Director CAA | (+230) 6032000 | civil-aviation@mail.gov.mu
Operational OJT on going. Awaiting to commence testing with other ANSP and airspace users as they become ready. Missing FPL. Transit times - no problems. Clock linked to ATC system GPS. FPL from Dubai with a 7 min time dif. Manual check also done DLY. issue with UAE flights from Dubai. Trend, for a few days at a time then ok for a while. lesser extent HAJJ flights from Jeddah no FPL. ICAO regional office to provide FIMM with feedback as to who are having challenges with FPL from FIMM.
FLLS | Zambia | yes | Ubitech | yes(new) | 2012-07-01 | 2012-08-01 | 2012-09-01 | Aug/Sep 2012 | August/September 2012 | no | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2012-11-15 | Stanley Sitali / Jacqueline Malambo | (+260) 211271195 / © 977495215 / © 95282971 | stanley.sitali@lun.aero / jacqueline.malambo@lun.aero
Back up terminal for manual operations in the process of being acquired. Should be installed by end of June 2012. Missing FPL. Clock auto update with GPS. Old AFTN switch that is sometimes down. Replacement work is underway. Switch also linked to AIM system, but sometimes do not exchange info. Comm. link - local telecom unreliable on leased lines. moving to fibre optic and VPN internet several possible service providers. internal processes - standard operations, don't see DLA here. Service messages are automated, only problem when system is down.
FMMI | Madagascar
Not in attendance
FNLU | Angola
Not in attendance
FQMA | Mozambique | no | Copperchase | yes | 2012-06-30 | 2012-07-25 | 2012-07-30 | 2012-08-01 | 2012-08-01 | no | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2012-11-15 | Joana Agostinho / Dalilo A Amade | (c)(+258) 826516230 /© 828958570 | jomutimba@gmail.com / daliloamade@yahoo.com.br
No further comments. MISSING FPL - clocks - FQMA MANUAL CLOCKS VERIFIED AGAINST FQBR which has GPS clock. Transit times - within the same min. Links - VSAT to FAJS no main problems. Internal lines sometimes challenging moving to domestic VSAT with local telecom to improve reliability. internal system delays - RELATED TO NETWORK CHALLENGES. response to messages - NO ISSUES.
FSIA | Seychelles
Information AVBL from the Kenya FCWM report
FVHA | Zimbabwe | yes | Comsoft | yes | 2012-06-01 | 2012-06-01 | 2012-06-01 | 2012-06-01 | 2012-07-01 | yes | Radar system FDP decommissioned as of 15 Nov 2012 | n/a | n/a | n/a | n/a | n/a | n/a | 2012-08-01 | 2012-11-15 | Caleb Furawo / Erick Chavunduka | (+263) 4585006 / ©772422031 / © 712867855 | cfurawo@caaz.co.zw / erick@caaz.co.zw
Radar system upgrade/replacement due to take place from 2013. Current ATM Operations will use the Comsoft AMHS strip printers in the interim compliant to FPL 2012. MISSING FPL - clocks - auto GPS sync. Transit time - within the same min. Comm. Links - VPN network and VSAT network links reliable. internal SYSTEM DELAYS - none. Response to messages - manual response from queued messages.
FWLL | Malawi | YES | Technobrain | yes | 2012-06-15 | 2012-07-01 | 2012-07-30 | 2012-08-01 | 2012-08-01 | yes | yes | Technobrain | same as AIM system | same as AIM system | same as AIM system | same as AIM system | same as AIM system | September/October 2012 | 2012-11-15 | Dixie Kwatani / MFT Bongwe | (+265) 888892494 / ©1770577 / 888867654 / © 1770577 | dkwatani@yahoo.co.uk / donchimtengo@yahoo.com
Will move in line with ATNS VSAT transmission dates. Full commitment from Government in support of this project received in March 2012. - missing FPL - CLOCKS AUTO SYNC WITH GPS. Transit time - no problem. Comm. links - leased lines reliable internal systems delays - NO ALARM TO ALER opr OF MESSAGES in queue, power system unreliable and can cause delays.response to messages - human attitude to responding to messages needs attention.
FXMM | Lesotho | no | VSAT - ATNS | YES | 2012-06-01 | 2012-06-01 | 2012-06-01 | 2012-07-01 | 2012-09-01 | no | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2012-09-01 | 2012-11-15 | Ntsontso Joseph Molefi / Jacob Lesekele | (+266) 22350115 / © 58077517 / 22350362 / © 58489404 | jomolefi@graduate.org / jacoblesekele@hotmail.com
No further comments. Missing FPL - INTERNAL CLOCKS automatic sync with GPS. Transit delays - not experienced. Comm. links - STABLE /AVBL. INTERNAL SYSTEM DELAYS - none. QUERIES - no problems.
FYWH | Namibia | no | Copperchase UK | yes | completed | completed | operational | 2012-06-01 | 2012-07-01 | yes | no | THALES / converter (Copperchase) | 2012-07-01 | 2012-07-01 | 2012-07-01 | 2012-07-01 | 2012-07-01 | 2012-08-01 | 2012-11-15 | Veronica Kandjabanga-Adeyeye / Hilma Leonard | (+264) 61702080 / © 812470437 / © 812455813 | adeyeyev@dca.com.na / caiso@dca.com.na
Installing a Copperchase converter between AFTN and Eurocat X. missing FPL. - clocks - auto sync GPS. Transit times - within the same min. Comm. Links - local telecoms lines some LAN some dial up and some on fibre. Internal system delays - none. Response to messages - no challenges. Namibia to send ICAO regional office a copy of procedures around missing FPL by end of May 2012.
FZAA | Congo
Not in attendance
HBBA | Burundi | no | VSAT - ATNS | YES | 2012-06-01 | 2012-06-01 | 2012-06-01 | 2012-06-01 | 2012-07-01 | no | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2012-09-01 | 2012-11-15 | Diomede Ntawuhanakanka | (+257) 78818747 | diontawuhana@yahoo.fr
No further comments. Missing FPL. Clocks - auto sync with GPS. Will confirm this to ICAO regional office by 18 May 2012. Transit times - Kenya messages 14 mins out. Comm.. Links - VSAT to FAJS. Flight from East Congo do not have FPL. Internal sys delays - manual system. Response to messages - no issue.
HRYR | Rwanda
Not in attendance
HTDA | Tanzania | yes | Egisavia | yes | 2012-05-01 | June/July 2012 | 2012-09-30 | Aug/Sep 2012 | August/September 2012 | yes | yes | Egisavia | same as AIS system | same as AIS system | same as AIS system | same as AIS system | same as AIS system | August/September 2012 | 2012-11-15 | Simon Kessy / Ali Chang'a | (+255) © 754403082 /© 755283680 | skessy@tcaa.go.tz / achanga2004@yahoo.co.uk
Challenge that there is no backup system for AFTN. Missing FPL: clock is GPS sync via network. Transit times are a few seconds time stamp is the same. Comm. links Telecomm company lines are unreliable and take long to repair. This contributes to delays in distribution to ATSU's. Telecomm company network infrastructure is vulnerable thus moving to fibre-optic lines. system generates an error with EOBT and ETD, FPL is rejected, this will be addressed with upgrade. Training/co-operation, Tanzania to inform ICAO regional office WI 7 days
Inter regional hub connections
Action Items for all states:
Provide training plan to ICAO
Keep ICAO informed re implementation status
Inform ICAO regarding contact person and details and keep them up to date
States to indicate to ICAO regional office that procedures around message handling are in place and are applicable and current and in use. 30 May 2012.
States to communicate by e-mail to the focal points what ATM/CNS systems are in use.
States to advise ICAO regional office and copy participants what IAIP (AIP, AMENDMENT, AIP SUP and AIC) do you have and when was last updated. By 30 May 2012.
VVIP flights - FPL are filed incorrectly (wrong DEP and times etc) FPL laps etc. this needs to be passed to the FPL TF and ask sub group for regional guidance.
As states are ready for testing they are to formally advise the applicable state via e-mail and formal test procedures will be agreed to with specific dates, times and conditions.
ICAO regional office to provide states with an AIC example re fell 2012. www.eurocontrol.int web page provides good guidance material (AIC and Training)
Missing flight plans common problems
Unsynchronised clocks
Delayed transit times
Communication links
Internal system delays
Lack of proper use of service message (RQP/RQS)
No response to query messages
Air Navigation Issues/challenges that impact on FPL -
Zambia - investment in the CNS/ATM infrastructure is challenging despite it being necessary with legacy systems. There is an investment plan in place for the next 5 years.
Swaziland - is currently disposing of legacy equipment that may be useful to other states. Interested states can approach Swaziland and discuss co-operation. It is suggested that on a regional bases we should be aware of who shares similar systems for possible co-operation.
Botswana - communication from ICAO regional office tends to be received late. ICAO informed that states (DG OFFICES) acknowledge receipt of the documents, however they do not seem to filter to the necessary, applicable persons. FPL 2012 focal points are also sent a copy of the invite.
Lesotho - there is a challenge around a requirement for more staff. Challenges around international travel approval and attendance of important meetings.
Malawi - attendance of meetings is not always the correct person( the one who does the job) and they do not train/pass on the information. Task is delegated to someone else who has to work from documentation.
Zimbabwe - lack of knowledge on new terms such as PBN etc… suggesting a new training module to address this challenge. Encourage engineering staff to interact without ICAO facilitation.
Mozambique - the AIS to AIM transmission, there needs to be more localised, sub regional workshops to improve understanding and address challenges
Namibia - applicable ICAO communication doesn’t seem to make it to the applicable people.
Burundi - training for staff is a challenge.
South Africa - the lack of on time aeronautical information