## Slide 1
Presented on by: François-Xavier SALAMBANGA
Regional Officer CNS ICAO WACAF
Key Phases of the Peer Review Programme
Module 2
Workshop on the Manual of AFI ANSPs Peer Review
Grand Bassam, Côte d’Ivoire 26-27 April 2018

## Slide 2: Outline
Preparation
On site review
Reporting
Implementation and monitoring

## Slide 3
Preparation phase
Programme Management Team (MT) to:
Confirm the scope and duration of the activity;
Confirm the assignments of the TL and all TMs
Programme Phases

## Slide 4
Preparation phase
Programme Management Team (MT) to:
Request the release of all TMs, including short-term seconded reviewers and SMEs;
Review information and documents submitted by the Host ANSP (Response Plans/CAPs and associated evidence, self-assessment results…)
Programme Phases

## Slide 5
Preparation phase
Programme Management Team (MT) to:
Prepare Host ANSP-specific activity plan and coordinate with TMs;
Coordinate Travel arrangements
Programme Phases

## Slide 6
Preparation phase
Programme Management Team (MT) to:
Manage various administrative issues;
Conduct a Team briefing.
Programme Phases

## Slide 7
Preparation phase
The Host ANSP to:
a) Conduct PQs self-assessment;
b) Ensure that Response Plans/CAPs related to not satisfactory PQs within the scope of the activity are fully implemented and updated
Programme Phases

## Slide 8
Preparation phase
The Host ANSP to:
Prepare, update and organize evidence and documentation to be submitted to the activity team, including manuals and/or procedures, records, etc.;
Communicate with the TL in a timely manner and provide him with all required information and documentation;
Support the TL with travel, transportation and administrative issues and information
Programme Phases

## Slide 9
On site review phase
RT visit Host ANSP to :
Conduct a systematic and objective assessment of the Host ANSP procedures and processes;
Recommend the issuance of any new observation to address identified deficiencies;
Collect and document evidence submitted by the Host ANSP;
Inform the Host ANSP of the outcome of the review during a closing meeting or briefing between the RT and Host ANSP.
Programme Phases

## Slide 10
On site Review
The Host ANSP to :
Ensure the availability of it representatives, counterparts and staff members involved;
Makes the evidence, information and documentation requested readily available to be submitted in a timely manner
Programme Phases

## Slide 11
On site Review
The Host ANSP to :
Facilitate and arrange visits to industry and/or service providers;
Provide a suitable working environment for the activity team;
Arranges daily transportation and administrative issues, as required.
Programme Phases

## Slide 12
  Reporting Phase
TL submits draft report of the onsite activity, compiled from contributions and notes from each TM;
RT performs a quality and technical review of the review results (i.e. the observations issued by each TM) and the input of each TM to the review draft report;
RT produces the draft report and sends it to the Host ANSP for comments
Programme Phases

## Slide 13
  Reporting Phase
RT reviews the Host ANSP’s comments for incorporation in the final report;
MT sends the final activity report to the Host ANSP at the end of this phase;
MT & RT assess Response Plans/CAPs submitted by the Host ANSP to ensure that they are acceptable and that they fully address associated PQs observations.
Programme Phases

## Slide 14
  Reporting Phase
Host ANSP to:
Provide comments to the draft report within two (2) weeks on receipt of the draft review report;
Develop an acceptable Response Plan/CAP in response to review observations;
Submit the Response/CAPs to the MT two (2) weeks on receipt of the final report.
Programme Phases

## Slide 15
  Reporting Phase
MT to:
Assess the submitted Response Plans/CAPs to ensure their relevance to address associated PQs observations;
Provide comments on unsatisfactory CAPs to the Host ANSP for revision and resubmission;
Notify the acceptance of the final Response CAPs to the Host ANSP
Programme Phases

## Slide 16
  Implementation & Monitoring
Host ANSP to:
Submit revised Response Plans/CAPs to MT
Start implementing the corrective actions outlined in each CAP;
Programme Phases

## Slide 17
  Implementation & Monitoring
Host ANSP to regularly:
Update to MT any change in Response Plans/CAPs;
Provide MT with relevant and complete evidence of implementation
Programme Phases

## Slide 18
  Implementation & Monitoring
MT to regularly:
Assess the proposed change in Host ANSP Response Plans/CAPs;
Monitor the Host ANSP’s progress in implementing its Response Plans/CAPs
Programme Phases

## Slide 19
“We know where to go”